Chapter 6: Managing IS Projects and Creating IS Solutions

Critical Pre-Development Questions

- Concept and inception stages

  - What are we planning and why?  begin to understand high level system requirements and also the business case (feasibility study)

  - Is the project feasible?  study, technical, financial feasibility

    - Cost-benefits analysis

      - Internal Labour Cost, Capital Costs, Expected life span of the system, productivity savings, Customer Satisfaction, Brand Image

  - Should we build or buy/lease? Is there time?

    - Request for Information: gather information about a product/ vendor capabilities

      - Followed by a request for proposal (more detailed)  starts bidding

  - If we build, should we do it in-house or outsource it?

The Stages and Importance of the System Development Life Cycle (SDLC)

- SDLC: used for the stages and activities of system development

- Four pillars  1. People 2) right tools 3) methods to build the system 4) management

- Concept: foster an environment that promotes ideas that can improve ROI

- Inception: begins with an idea. Focus is on understanding the problem to be solved or opportunity to be addressed (early interactions with stakeholders to complete business case)

- Elaboration: Finalize the requirements for the system and the project plan, designs the system architecture  create conceptual models of the systems and subsystems

- Construction: build the initial running system  implement core functionalities

- Transition: finalizes the system, tests it, and puts it in place (final training of users and management of users)

- Production: continuously monitor, maintain, and evaluate the system

- Retirement: concept of new system to replace old one

Managing an IS Project

- Project Management: the application of knowledge skills, tools, and techniques to project activities to meet project requirements

- Oversees three main project elements: scope, resources, time

  - Does it follow organizational strategy?

Overview of Project Management Tasks

- May occur as early as the concept phase

- Normally begin at the point where the organization has approved a project proposal and selected it to be executed as part of their project portfolio

- Nine key PM components

- Scope management

- Time management

- Cost management

- Quality Management

- Others  HR, Risk, Procurement, Communications

Project Time Management

- After budgeting, the most important function for PM is project schedule

- Define activities – identify the activities required to produce project deliverables

- Sequence activities – identify and document relationships between project activities

- Estimate activity resources – estimate type and quantity of material, people, equipment, or supplies required by each activity

- Estimate activity durations – approximate the number of work periods needed to complete individual work activities with estimated resources

- Develop Schedule – analyze activity sequences, durations, resource requirements, and schedule constraints to create project schedule activities

- Control Schedule – monitor the status of the project to update project progress and managing changes to the schedule baseline

- Gantt Chart: standard format for displaying the results of the first four time-management

Project Risk Management

- Risk assessment and risk control

Project Management Office (PMO)

- Provide standards and best practices for all projects

- Facilitate, monitor, and report on the project portfolio

  - PMO will track the status of projects and facilitate any necessary changes to projects

Project Management Software

- PM Software – designed to support and automate project management and decision-making tasks

  - Low-level packages – entry-level users, basic scheduling, project control, reporting, etc.

  - Mid-level software – adds to these functions by providing resource-leveling, resource-allocation, cost-control, and flexible-charting capabilities; allows for effective management of large projects, 2000 tasks

  - High-level software – provides advanced functions including scheduling by user-defined rules, programming languages, resource management for multiple projects, and risk management  identify conflicting demands and allow manager to set priorities

- Program evaluation review technique (PERT)  schedule and manage the tasks within a project

  - Critical path!  shit that has to be done

IS Development Teams

- 2 people involved with an IS project

  - On actual project team  stakeholders in the IS

Importance of Stakeholders

- SME  subject matter expert

- Stakeholder Analysis: begin with this in feasibility study  stakeholders know their shit

- List of stakeholders, what each has at stake, the degree of impact they have on project

A Typical IS Project Team

  - Project Sponsor – project goals go with organization’s business objectives

    - Considers the strengths and weaknesses of the business and team  identify opportunities and threats, understand financial aspects, manage risk

  - Project Manager (PM) – knowledge of methods and techniques to ensure delivery of the project on time and on budget, primary liaison w/ project sponsor and project steering

  - Account Management – development team when outsourcer  sales and service of team  initial point of contact to client

  - Architecture and Design – proposed system is architecturally sound

  - Analysts – high level requirements into lower levels of detail

  - Developers – creates system

  - Specialists – SMEs

  - Client Interface

- Project Steering Committee – ensures all goals, budgets, etc are met. (Project sponsor, CFO, smg)

Standard IS Methodology

The Traditional IS Methodology: The Waterfall Model

- See Table 6.7, Page 237 for advantages and disadvantages

Modern IS Methodologies

- Evolutionary Model: investigate, specify, and implement core part of the system with minimal functionality

  - Team tests then evaluates this version of the system to plan for the next one

    - Keep adding new shit

- Agile Development  in between evolutionary and waterfall

IS Modelling

- UML Diagrams (Unified Modelling Language)

  - Good for developing object-oriented systems

  - Consists of several graphic elements that form a set of diagrams when combined

  - Shows multiple views of a system  set of ULM diagrams = system model

- Use case  captures all possible ways to use a system

  - Which users employ which use cases as a tool for determining user requirements

IT Tools for IS Development

IS Development Tools

- Integrated Development Environments (IDEs)

  - Allows developers to complete several programming tasks within the same software application  Microsoft visual studio

- Modelling Tools and Code Generators

  - Important activity in info sys development

  - Code Generation: developer can use graphic diagrams to define a system’s components and how they relate

    - Clicking a button allows you to develop code corresponding to diagram m

- CASE Tools (Computer-Aided Software Engineering)

  - Support creation and maintenance of the many documents, diagrams, and data that the project team creates over the course of the IS life cycle and integrates into CASE environ.