BUSI 3309 Project Management

ASSIGNMENT # 2 – PARTIAL SOLUTION

# Question 1 (20 points)

(b)

EV(1) = Max (0, 27) = 27

Course of action: try pilot; if pilot works, build plant – EV (build) =

$64.00; if pilot does not work, do not build plant – EV = $0.00

(c)  EVSI = EV(2) – EV(5) = 27 – 0 = 27

Question # 2 (15 points)

We would expect to be penalized for one day past the 15 day deadline

# Question 4 (30 points)

(a)

Critical Path: B‐E‐H‐J

Expected project completion time = 26 weeks  Variance = 4.11 weeks

- P(T  25) = P(Z  ‐0.49) = 0.3121

- Eexpected project completion time = 21.38 weeks

## (d) Xj = Earliest Starting Time of Activity j

Minimize Z = XA + XB + XC + XD + XE + XF + XG + XH + XI + XJ

Subject to:

| XD ≥ XA + 4 |  | XD ≥ XC | + 5 |  |  |
| --- | --- | --- | --- | --- | --- |
| XC ≥ XB + 4 |  |  |  |  |  |
| XE ≥ XB + 4 |  |  |  |  |  |
| XF ≥ XB + 4 |  |  |  |  |  |
| XD ≥ XA + 4 |  |  |  |  |  |
| XG ≥ XE + 10 |  |  |  |  |  |
| XH ≥ XE + 10 |  |  |  |  |  |
| XI ≥ XG + 6 |  | XI ≥ XD | + 3 |  |  |
| XJ ≥ XH + 7 |  | Xj ≥ XF | + 9 |  |  |
| All variables ≥ 0 |  |  |  |  |  |

## Wj = Latest Starting Time of Activity j

Maximize Z = WA + WB + WC + WD + WE + WF + WG + WH + WI + WJ Subject to:

| WD ≥ WA + 4 |  | WD ≥ WC + 5 |  |  |  |
| --- | --- | --- | --- | --- | --- |
| WC ≥ WB + 4 |  |  |  |  |  |
| WE ≥ WB + 4 |  |  |  |  |  |
| WF ≥ WB + 4 |  |  |  |  |  |
| WD ≥ WA + 4 |  |  |  |  |  |
| WG ≥ WE + 10 |  |  |  |  |  |
| WH ≥ WE + 10 |  |  |  |  |  |
| WI ≥ WG + 6 |  | WI ≥ WD + 3 |  |  |  |
| WJ ≥ WH + 7 |  | Wj ≥ WF + 9 |  |  |  |
| WJ + 5 = max (Xj + 5, XI + 3) |  |  | WI + 3 = max (Xj + 5, XI + 3) |  |  |
| All variables ≥ 0 |  |  |  |  |  |