Chapter 4: Project Integration Management

TRUE/FALSE

1.	In project integration management, directing and managing project execution involves carrying out the project management plan by performing the activities included in it.

ANS:	T

Directing and managing project work involves carrying out the project management plan by performing the activities included in it. The outputs of this process are deliverables, work performance information, change requests, project management plan updates, and project documents updates.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.140

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Comprehension

2.	Interface management involves identifying and managing the points of interaction between various elements of a project.

ANS:	F

Interface management nvolves identifying and managing the points of interaction between various elements of a project.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.142

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Comprehension

3.	The number of interfaces in a single project is limited, and does not depend on the number of people involved in the project.

ANS:	F

Project integration management includes interface management, which involves identifying

and managing the points of interaction between various elements of a project. The number of interfaces can increase exponentially as the number of people involved in a project increases.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.142

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Comprehension

4.	Project integration management must occur just within the context of a particular project.

ANS:	F

Project integration management must occur within the context of the entire organization, not just within a particular project.The project manager must integrate the work of the project with the ongoing operations of the organization.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.142

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

5.	A SWOT analysis, being a linear process, cannot be performed using the nonlinear mind mapping technique.

ANS:	F

Some people like to perform a SWOT analysis by using mind mapping, a technique that uses branches radiating from a core idea to structure thoughts and ideas.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.144

OBJ:	LO:4-2	NAT:	BUSPROG: Analytic

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

6.	An organization’s information technology project selection process should guide the strategic plan.

ANS:	F

Aligning IT projects with business strategy is consistently a top concern for CIOs. Most organizations face thousands of problems and opportunities for improvement. Therefore, an organization’s strategic plan should guide the IT project selection process.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.146

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

7.	Information systems can help an organization support a strategy of being a low-cost producer.

ANS:	T

Many information systems are classified as “strategic” because they directly support key business strategies. For example, information systems can help an organization support a strategy of being a low-cost producer.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.147

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

8.	Projects that address broad organizational needs are likely to fail.

ANS:	F

Projects that address broad organizational needs are much more likely to be successful because they will be important to the organization.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.148

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

9.	As projects progress, the organization must reevaluate the need, funding, and will for each project to determine if the project should be continued, redefined, or terminated.

ANS:	T

As projects progress, the organization must reevaluate the need, funding, and will for each project to determine if it should be continued, redefined, or terminated.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.148

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

10.	Opportunities and directives are essentially the same thing.

ANS:	F

Opportunities are chances to improve the organization.Directives are new requirements imposed by management, government, or some external influence.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.149

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

11.	Projects that arise as a result of problems and directives must be resolved quickly to avoid hurting an organization’s business.

ANS:	T

It is often easier to get approval and funding for projects that address problems or directives because the organization must respond to these categories to avoid hurting their business.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.149

OBJ:	LO:4-2`	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

12.	The organization should complete low-priority projects before high-priority ones, if the low-priority ones take less time.

ANS:	F

Organizations can also categorize IT projects as having high, medium, or low priority based on the current business environment. An organization should always complete high-priority projects first, even if a low- or medium-priority project could be finished in less time.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.149

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

13.	An organization should consider only projects with a negative NPV if financial value is a key criterion for project selection.

ANS:	F

An organization should consider only projects with a positive NPV if financial value is a key criterion for project selection.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.150

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

14.	NPV analysis is a method for making equal comparisons between cash flows for multi-year projects.

ANS:	T

NPV analysis is a method for making equal comparisons between cash flows for multi-year projects.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.150

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

15.	An annual discount factor is a multiplier for each year based on the discount rate and year.

ANS:	T

The annual discount factor is a multiplier for each year based on the discount rate and year.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.152

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

16.	The ROI is always positive.

ANS:	F

The ROI is always a percentage. It can be positive or negative.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.152

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

17.	Payback period is the amount of time it will take to recoup, in the form of net cash inflows, the total dollars invested in a project.

ANS:	T

Payback analysis is another important financial tool when selecting projects. Payback period is the amount of time it will take to recoup the total dollars invested in a project, in terms of net cash inflows.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.153

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

18.	A project charter typically does not authorize the project manager to use organizational resources to complete the project.

ANS:	F

A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management. It authorizes the project manager to use organizational resources to complete the project.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.157

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

19.	Some organizations initiate projects using a contract in place of a project charter.

ANS:	T

Instead of project charters, some organizations initiate projects using a simple letter of agreement, while others use much longer documents or formal contracts.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.157-158

OBJ:	LO: 4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

20.	The introduction or overview of a project must only include a list of definitions and acronyms.

ANS:	F

The introduction or overview of the project should include the following information: the project name; a brief description of the project and the need it addresses; the sponsor’s name; the names of the project manager and key team members; deliverables of the project; a list of important reference materials; and a list of definitions and acronyms.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.161-162

OBJ:	LO: 4-5	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Knowledge

21.	A Gantt chart is the same as a project management plan.

ANS:	F

The project management plan is much more than a Gantt chart.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.164

OBJ:	LO:4-4	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Comprehension

22.	It is necessary that IT project managers have prior technical experience in creating and managing IT products.

ANS:	F

It is often helpful for IT project managers to have prior technical experience or at least a working knowledge of IT products.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.167

OBJ:	LO:4-5	NAT:	BUSPROG: Technology

TOP:	Directing And Managing Project Work		KEY:	Bloom's: Comprehension

23.	Corrective actions reduce the probability of negative consequences associated with project risks, while preventive actions should result in improvements in project performance.

ANS:	F

Corrective actions should result in improvements in project performance. Preventive actions reduce the probability of negative consequences associated with project risks.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.171

OBJ:	LO:4-6	NAT:	BUSPROG: Technology

TOP:	Monitoring And Controlling Project Work		KEY:	Bloom's: Comprehension

24.	Change requests are always made in writing.

ANS:	T

Change requests are common on projects and occur in many different forms. They can be oral or written, formal or informal.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.171

OBJ:	LO:4-7	NAT:	BUSPROG: Technology

TOP:	Performing Integrated Change Control		KEY:	Bloom's: Comprehension

25.	Organizational process asset updates are an important output of the closing process of a project.

ANS:	T

The project team should provide a list of project documentation, project closure documents, and historical information produced by the project in a useful format. This information is considered a process asset.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.175

OBJ:	LO:4-8	NAT:	BUSPROG: Technology	TOP:	Closing Projects Or Phases

KEY:	Bloom's: Knowledge

MULTIPLE CHOICE

1.	_____ involves working with stakeholders to create the document that formally authorizes a project.

| a. | Developing the project charter |
| --- | --- |
| b. | Developing the preliminary project scope statement |
| c. | Developing the project management plan |
| d. | Performing integrated change control |

ANS:	A

Developing the project charter involves working with stakeholders to create the document that formally authorizes a project —the charter.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.140

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

2.	_____ involves coordinating all planning efforts to create a consistent, coherent document.

| a. | Developing the project charter |
| --- | --- |
| b. | Developing the preliminary project scope statement |
| c. | Developing the project management plan |
| d. | Developing the organizational process assets updates |

ANS:	C

Developing the project management plan involves coordinating all planning efforts to create a consistent, coherent document—the project management plan.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.140

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

3.	The outputs of the _____  process include change request status updates, project management plan updates, and project document updates.

| a. | initiating |
| --- | --- |
| b. | planning |
| c. | executing |
| d. | monitoring and controlling |

ANS:	D

The outputs of the monitoring and controlling process include change request status updates, project management plan updates, and project document updates.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.141

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

4.	The first step in the planning process is _____.

| a. | to tie the information technology strategic plan to the organization’s overall strategic plan | c. | to start defining potential IT projects in terms of their scope, benefits, and constraints |
| --- | --- | --- | --- |
| b. | to perform a business area analysis | d. | to choose which projects to do and assigning resources to work on them |

ANS:	A

The first step in the planning  process, starting at the top of the hierarchy, is to tie the IT strategic plan to the organization’s overall strategic plan.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.145

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

5.	The _____  stage of information technology planning outlines business processes that are central to achieving strategic goals and helps determine which ones could most benefit from information technology.

| a. | project planning |
| --- | --- |
| b. | business area analysis |
| c. | resource allocation |
| d. | information technology strategy planning |

ANS:	B

The business area analysis outlines business processes that are central to achieving strategic goals and helps determine which processes could most benefit from IT.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.145

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

6.	In the _____ stage of selecting information technology projects, organizations define project scope, benefits, and constraints.

| a. | project planning |
| --- | --- |
| b. | business area analysis |
| c. | resource allocation |
| d. | information technology strategy planning |

ANS:	A

In the project planning stage of selecting information technology projects, organizations define project scope, benefits, and constraints.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.146

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

7.	In the _____ stage of selecting information technology projects, organizations select information technology projects.

| a. | project planning |
| --- | --- |
| b. | business area analysis |
| c. | resource allocation |
| d. | information technology strategy planning |

ANS:	C

In the resource allocation stage of selecting information technology projects, organizations select information technology projects.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.146

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

8.	_____ are new requirements imposed by management, government, or some external influence.

| a. | Opportunities | c. | Problems |
| --- | --- | --- | --- |
| b. | Charters | d. | Directives |

ANS:	D

Directives are new requirements imposed by management, government, or some external influence.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.149

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

9.	_____ analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time.

| a. | Cost of capital | c. | Cash flow |
| --- | --- | --- | --- |
| b. | Net present value | d. | Payback |

ANS:	B

Net present value (NPV) analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.149-150

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

10.	Benefits minus costs is known as the _____.

| a. | cost of capital | c. | discount factor |
| --- | --- | --- | --- |
| b. | cash flow | d. | opportunity cost of capital |

ANS:	B

Cash flow is the benefits minus costs or income minus expenses.

PTS:	1	DIF:	Difficulty: Easy		REF:	p. 150

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

11.	The first step in determining the NPV is to _____.

| a. | determine the estimated costs and benefits for the life of the project and the products it produces |
| --- | --- |
| b. | determine the discount rate |
| c. | calculate the net present value |
| d. | determine the cash flow |

ANS:	A

The first step in determining the NPV is to calculate the estimated costs and benefits for the life of the project and the products it creates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.151

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

12.	Which of the following is true of return on investment or ROI?

| a. | It is always a percentage. | c. | It is the result of adding the project costs to the profits. |
| --- | --- | --- | --- |
| b. | It is always a positive number. | d. | The lower it is, the better. |

ANS:	A

The ROI is always a percentage. It can be positive or negative.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.152

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

13.	The _____ is the minimum acceptable rate of return on an investment.

| a. | capitalization rate | c. | discount rate |
| --- | --- | --- | --- |
| b. | internal rate of return | d. | required rate of return |

ANS:	D

The required rate of return is the minimum acceptable rate of return on an investment.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.153

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

14.	Payback occurs when:

| a. | the net cumulative benefits minus costs equal one. | c. | the net costs are lower than the cumulative benefits. |
| --- | --- | --- | --- |
| b. | the net cumulative benefits equal the net cumulative costs. | d. | the cumulative benefits are double the cumulative costs. |

ANS:	B

Payback occurs when the net cumulative benefits equal the net cumulative costs, or when the net cumulative benefits minus costs equal zero.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.153

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

15.	A project’s internal rate of return can be determined by finding what discount rate results in an NPV of _____ for the project.

| a. | zero | c. | a hundred percent |
| --- | --- | --- | --- |
| b. | one | d. | fifty percent |

ANS:	A

You can determine a project’s internal rate of return (IRR) by finding what discount rate results in an NPV of zero for the project.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.153

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

16.	In a weighted scoring model, the sum of the weights of all the criteria must total _____ percent.

| a. | 10 | c. | 100 |
| --- | --- | --- | --- |
| b. | 50 | d. | 150 |

ANS:	C

In a weighted scoring model,  a weight is assigned to each criterion based on its importance to the project. Determining weights requires consultation and final agreement. You can assign weights based on  percentages; the weights of the criteria must total 100 percent.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.155

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

17.	 A _____ is a document that recognizes the existence of a project and provides direction on the project’s objectives and management.

| a. | stakeholder register | c. | directive |
| --- | --- | --- | --- |
| b. | risk register | d. | project charter |

ANS:	D

A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.157

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

18.	The business case includes information on _____.

| a. | the business need for the project | c. | the project objective, high-level requirements, and time and cost goals |
| --- | --- | --- | --- |
| b. | relevant government or industry standards | d. | policies, procedures, guidelines, and systems that influence a project’s success |

ANS:	C

Many projects require a business case to justify their investment. Information in the business case, such as the project objective, high-level requirements, and time and cost goals, is included in the project charter.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.158

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

19.	Which of the following are organizational process assets?

| a. | Management systems | c. | Government standards |
| --- | --- | --- | --- |
| b. | The organization’s infrastructure | d. | Marketplace conditions |

ANS:	A

Organizational process assets include formal and informal plans, policies, procedures, guidelines, information systems, financial systems, management systems, lessons learned, and historical information that can influence a project’s success.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.158

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

20.	A _____ is a document used to coordinate all project planning documents and help guide a project’s execution and control.

| a. | project management plan | c. | scope statement |
| --- | --- | --- | --- |
| b. | statement of work | d. | business case |

ANS:	A

A project management plan is a document used to coordinate all project planning documents and help guide a project’s execution and control.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.161

OBJ:	LO:4-4	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Knowledge

21.	The _____ section of the project plan should describe the major project functions and activities and identify those individuals who are in charge of them.

| a. | organizational charts |
| --- | --- |
| b. | other organizational or process-related information |
| c. | project responsibilities |
| d. | management objectives |

ANS:	C

This section of the project plan should describe the major project functions and activities and identify the people responsible for them. A responsibility assignment matrix is often used to display this information.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.162

OBJ:	LO:4-4	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Knowledge

22.	The _____ section of the project management plan describes how to monitor project progress and handle changes.

| a. | management objectives | c. | risk management |
| --- | --- | --- | --- |
| b. | project controls | d. | technical processes |

ANS:	B

The project controls section describes how to monitor project progress and handle changes. Will there be monthly status reviews and quarterly progress reviews? Will there be specific forms or charts to monitor progress?

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.163

OBJ:	LO:4-4	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Knowledge

23.	The project schedule information section of the project management plan includes ____.

| a. | a detailed budget | c. | an elaborate timetable |
| --- | --- | --- | --- |
| b. | a list of key deliverables | d. | a directory of staff involved in the project |

ANS:	C

The project schedule information section should include a detailed schedule that provides more detailed information about the project schedule. It should reference the schedule management plan and discuss dependencies among project activities that could affect the project schedule.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.164

OBJ:	LO:4-4	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Knowledge

24.	The _____ section of the project management plan describes specific methodologies a project might use and explains how to document information.

| a. | management objectives | c. | risk management |
| --- | --- | --- | --- |
| b. | project controls | d. | technical processes |

ANS:	D

The technical processes section describes specific methodologies a project might use and explains how to document information.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.163

OBJ:	LO:4-4	NAT:	BUSPROG: Technology

TOP:	Developing A Project Management Plan		KEY:	Bloom's: Knowledge

25.	The majority of time on a project is usually spent on _____, as is most of the project’s budget.

| a. | execution | c. | closing |
| --- | --- | --- | --- |
| b. | planning | d. | monitoring and controlling |

ANS:	A

The majority of time on a project is usually spent on execution, as is most of the project’s budget.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.166

OBJ:	LO:4-5	NAT:	BUSPROG: Technology

TOP:	Directing And Managing Project Work		KEY:	Bloom's: Knowledge

26.	_____ should result in improvements in project performance.

| a. | Corrective actions | c. | Preventive actions |
| --- | --- | --- | --- |
| b. | Defect repairs | d. | Product acceptance plans |

ANS:	A

Corrective actions should result in improvements in project performance.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.166

OBJ:	LO:4-6	NAT:	BUSPROG: Technology

TOP:	Monitoring And Controlling Project Work		KEY:	Bloom's: Knowledge

27.	Which of the following is a proactive process undertaken to reduce the probability of negative consequences associated with project risks?

| a. | Performance reports | c. | Defect repairs |
| --- | --- | --- | --- |
| b. | Preventive actions | d. | Corrective actions |

ANS:	B

Preventive actions reduce the probability of negative consequences associated with project risks. The problem has not yet occurred. Measures are taken so that problems do not occur.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.171

OBJ:	LO:4-6	NAT:	BUSPROG: Technology

TOP:	Monitoring And Controlling Project Work		KEY:	Bloom's: Comprehension

28.	An IT company revises its process parameters in response to complaints from vendors that products were not ready on time. This would be an example of _____.

| a. | cost forecasting | c. | defect repairs |
| --- | --- | --- | --- |
| b. | a preventive action | d. | a corrective action |

ANS:	D

Corrective actions should result in improvements in project performance.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.171

OBJ:	LO:4-6	NAT:	BUSPROG: Technology

TOP:	Monitoring And Controlling Project Work		KEY:	Bloom's: Application

29.	A(n) _____ is a formal, documented process that describes when and how official project documents may be modified, the people authorized to make modifications, and the paperwork required for these changes.

| a. | WBS | c. | performance report |
| --- | --- | --- | --- |
| b. | project charter | d. | change control system |

ANS:	D

A change control system is a formal, documented process that describes when and how official project documents may be changed. It also describes the people authorized to make changes, the paperwork required for these changes, and any automated or manual tracking systems the project will use.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.173

OBJ:	LO:4-7	NAT:	BUSPROG: Technology

TOP:	Performing Integrated Change Control		KEY:	Bloom's: Knowledge

30.	_____ involves identifying and controlling the functional and physical design characteristics of products and their support documentation, and ensures that the descriptions of the project’s products are correct and complete.

| a. | NPV analysis | c. | Configuration management |
| --- | --- | --- | --- |
| b. | Project management information systems | d. | Project time management |

ANS:	C

Configuration management ensures that the descriptions of the project’s products are correct

and complete. It involves identifying and controlling the functional and physical design characteristics of products and their support documentation.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.173

OBJ:	LO:4-7	NAT:	BUSPROG: Technology

TOP:	Performing Integrated Change Control		KEY:	Bloom's: Knowledge

COMPLETION

1.	_____ involves coordinating all of the other project management knowledge areas throughout a project’s life cycle.

ANS:	Project integration management

PTS:	1	DIF:	Difficulty: Easy		REF:	p.140

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

2.	_____ involves identifying and managing the points of interaction between various elements of the project.

ANS:	Interface management

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.142

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

3.	_____ involves determining long-term objectives by analyzing the strengths and weaknesses, studying opportunities and threats, predicting future trends, and projecting the need for new products and services.

ANS:	Strategic planning

PTS:	1	DIF:	Difficulty: Easy		REF:	p.143

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

4.	A(n) _____ involves analyzing a company’s strengths, weaknesses, opportunities, and threats, and is used to aid in strategic planning.

ANS:	SWOT analysis

PTS:	1	DIF:	Difficulty: Easy		REF:	p.144

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

5.	_____  is a technique that uses branches radiating from a core idea to structure thoughts and ideas.

ANS:	Mind mapping

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.144

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

6.	_____ refer to undesirable situations that prevent an organization from achieving its goals.

ANS:	Problems

PTS:	1	DIF:	Difficulty: Easy		REF:	p.148

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

7.	_____ refer to chances to improve the organization.

ANS:	Opportunities

PTS:	1	DIF:	Difficulty: Easy		REF:	p.149

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

8.	_____ are new requirements imposed by management, government, or some external influence.

ANS:	Directives

PTS:	1	DIF:	Difficulty: Easy		REF:	p.149

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

9.	_____  analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time.

ANS:

Net present value

Net present value (NPV)

NPV

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.149-150

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

10.	A positive NPV means the return from a project exceeds the _____, the return available by investing the capital elsewhere.

ANS:	cost of capital

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.150

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Comprehension

11.	_____ is the result of subtracting the project costs from the benefits and then dividing by the costs.

ANS:

ROI

Return on investment

Return on investment (ROI)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.152

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

12.	The _____ is the discount rate that results in an NPV of zero for a project.

ANS:

internal rate of return

internal rate of return (IRR)

IRR

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.153

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

13.	A(n) _____ is a tool that provides a systematic process for selecting projects based on many criteria.

ANS:	weighted scoring model

PTS:	1	DIF:	Difficulty: Easy		REF:	p.154

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

14.	A(n) _____  is a methodology that converts value drivers, such as customer service, innovation, operational efficiency, and financial performance, to a series of defined metrics.

ANS:	balanced scorecard

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.156

OBJ:	LO: 4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

15.	_____ factors include relevant government or industry standards, the organization’s infrastructure, and marketplace conditions.

ANS:	Enterprise environmental

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.158

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

16.	_____ include formal and informal plans, policies, procedures, guidelines, information systems, financial systems, management systems, lessons learned, and historical information that can be used to influence a project’s success.

ANS:	Organizational process assets

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.158

OBJ:	LO: 4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

17.	_____ project work includes collecting, measuring, and disseminating performance information.

ANS:	Monitoring

PTS:	1	DIF:	Difficulty: Easy		REF:	p.169

OBJ:	LO:4-6	NAT:	BUSPROG: Technology

TOP:	Monitoring And Controlling Project Work		KEY:	Bloom's: Knowledge

18.	A(n) _____ is the approved project management plan plus approved changes.

ANS:	baseline

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.170

OBJ:	LO:4-6	NAT:	BUSPROG: Technology

TOP:	Monitoring And Controlling Project Work		KEY:	Bloom's: Knowledge

19.	_____ involves identifying, evaluating, and managing changes throughout the project life cycle.

ANS:	Integrated change control

PTS:	1	DIF:	Difficulty: Easy		REF:	p.171

OBJ:	LO: 4-7	NAT:	BUSPROG: Technology

TOP:	Performing Integrated Change Control		KEY:	Bloom's: Knowledge

20.	A(n) _____ is a formal group of people responsible for approving or rejecting changes to a project.

ANS:

change control board

change control board (CCB)

CCB

PTS:	1	DIF:	Difficulty: Easy		REF:	p.173

OBJ:	LO: 4-7	NAT:	BUSPROG: Technology

TOP:	Performing Integrated Change Control		KEY:	Bloom's: Knowledge

21.	A category of software that can help align projects with business strategy is called _____ tools.

ANS:

business service management

business service management (BSM)

BSM

PTS:	1	DIF:	Difficulty: Easy		REF:	p.176

OBJ:	LO: 4-9	NAT:	BUSPROG: Technology

TOP:	Using Software To Assist In Project Integration Management

KEY:	Bloom's: Knowledge

ESSAY

1.	List and briefly describe the six main processes involved in project integration management.

ANS:

1. Developing the project charter involves working with stakeholders to create the document that formally authorizes a project—the charter.

2. Developing the project management plan involves coordinating all planning efforts to create a consistent, coherent document—the project management plan.

3. Directing and managing project execution involves carrying out the project management plan by performing the activities included in it. The outputs of this process are deliverables, work performance information, change requests, project management plan updates, and project document updates.

4. Monitoring and controlling project work involves overseeing activities to meet the performance objectives of the project. The outputs of this process are change requests, project management plan updates, and project document updates.

5. Performing integrated change control involves identifying, evaluating, and managing changes throughout the project life cycle. The outputs of this process include change request status updates, project management plan updates, and project document updates.

6. Closing the project or phase involves finalizing all activities to formally close the project or phrase. Outputs of this process include final product, service, or result transition and organizational process assets updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.140-141

OBJ:	LO:4-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Integration Management?		KEY:	Bloom's: Knowledge

2.	What are the methods for categorizing information technology projects?

ANS:

Selecting projects is based on various categorizations, such as the impetus for the project, the time window for the project, and the general priority for the project.

The impetus for a project is often the need to respond to a problem, an opportunity, or a directive. Problems are undesirable situations that prevent an organization from achieving its goals. These problems can be current or anticipated. For example, users of an information system may be having trouble logging onto the system or getting information in a timely manner because the system has reached its capacity. In response, the company could initiate a project to enhance the current system by adding more access lines or upgrading the hardware with a faster processor, more memory, or more storage space. Opportunities are chances to improve the organization. For example, the project described in the opening case involves creating a new product that can make or break the entire company. Directives are new requirements imposed by management, government, or some external influence. For example, many projects involving medical technologies must meet rigorous government requirements.

Another categorization for information technology projects is based on the time it will take to complete a project or the date by which it must be done. For example, some potential projects must be finished within a specific time window. If they cannot be finished by this set date, they are no longer valid projects. Some projects can be completed very quickly—within a few weeks, days, or even minutes. Many organizations have an end user support function to handle very small projects that can be completed quickly. Even though many information technology projects can be completed quickly, it is still important to prioritize them.

Organizations can prioritize information technology projects as being high, medium, or low priority based on the current business environment. For example, if it is crucial to cut operating costs quickly, projects that have the most potential to do so would be given a high priority. The organization should always complete high-priority projects first, even if a low- or medium-priority project could be finished in less time. Usually there are many more potential information technology projects than an organization can undertake at any one time, so it is very important to work on the most important ones first.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.148-149

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

3.	What is a weighted scoring model? How is it created?

ANS:

A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria. These criteria can include factors such as meeting broad organizational needs; addressing problems, opportunities, or directives; the amount of time it will take to complete the project; the overall priority of the project; and projected financial performance of the project.

The first step in creating a weighted scoring model is to identify criteria important to the project selection process. It often takes time to develop and reach agreement on these criteria. Holding facilitated brainstorming sessions or using groupware to exchange ideas can aid in developing these criteria. Some possible criteria for information technology projects include:

• Supports key business objectives

• Has strong internal sponsor

• Has strong customer support

• Uses realistic level of technology

• Can be implemented in one year or less

• Provides positive NPV

• Has low risk in meeting scope, time, and cost goals

Next, you assign a weight to each criterion. Once again, determining weights requires consultation and final agreement. These weights indicate how much you value each criterion or how important each criterion is. You can assign weights based on percentages, and the sum of all of the criteria’s weights must total 100 percent. You then assign numerical scores to each criterion (for example, 0 to 100) for each project. The scores indicate how much each project meets each criterion. At this point, you can use a spreadsheet application to create a matrix of projects, criteria, weights, and scores. After assigning weights for the criteria and scores for each project, you calculate a weighted score for each project by multiplying the weight for each criterion by its score and adding the resulting values.

PTS:	1	DIF:	Difficulty: Challenging	REF:	p.154-155

OBJ:	LO:4-2	NAT:	BUSPROG: Technology

TOP:	Strategic Planning And Project Selection		KEY:	Bloom's: Knowledge

4.	What is a project charter? Discuss the inputs that can aid the development of a project charter.

ANS:

A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management. It authorizes the project manager to use organizational resources to complete the project. Ideally, the project manager provides a major role in developing the project charter.

The following inputs are helpful in developing a project charter:

• A project statement of work: A statement of work is a document that describes the products or services to be created by the project team. It usually includes a description of the business need for the project, a summary of the requirements and characteristics of the products or services, and organizational information, such as appropriate parts of the strategic plan, showing the alignment of the project with strategic goals.

• A business case: Many projects require a business case to justify their investment. Information in the business case, such as the project objective, high-level requirements, and time and cost goals, is included in the project charter.

• Agreements: If you are working on a project under contract for an external customer, the contract or agreement should include much of the information needed for creating a good project charter. Some people might use a contract or agreement in place of a charter; however, many contracts are difficult to read and can often change, so it is still a good idea to create a project charter.

• Enterprise environmental factors: These factors include relevant government or industry standards, the organization’s infrastructure, and marketplace conditions.Managers should review these factors when developing a project charter.

• Organizational process assets: Organizational process assets include formal and informal plans, policies, procedures, guidelines, information systems,financial systems, management systems, lessons learned, and historical information that can influence a project’s success.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.158

OBJ:	LO:4-3	NAT:	BUSPROG: Technology

TOP:	Developing A Project Charter	KEY:	Bloom's: Knowledge

5.	What is integrated change control? What are the main objectives of integrated change control?

ANS:

Integrated change control involves identifying, evaluating, and managing changes throughout the project life cycle. The three main objectives of integrated change control are:

1. Influencing the factors that create changes to ensure that changes are beneficial: To ensure that changes are beneficial and that a project is successful, project managers and their teams must make trade-offs among key project dimensions, such as scope, time, cost, and quality.

2. Determining that a change has occurred: To determine that a change has occurred, the project manager must know the status of key project areas at all times. In addition, the project manager must communicate significant changes to top management and key stakeholders. Top management and other key stakeholders do not like surprises, especially ones that mean the project might produce less, take longer to complete, cost more than planned, or be of lower quality than desired.

3. Managing actual changes as they occur: Managing change is a key role of project managers and their teams. It is important that project managers exercise discipline in managing the project to help minimize the number of changes that occur.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.171

OBJ:	LO:4-7	NAT:	BUSPROG: Technology

TOP:	Performing Integrated Change Control		KEY:	Bloom's: Knowledge