Chapter 5: Project Scope Management

TRUE/FALSE

1.	Scope refers to all the work involved in creating the products of the project and the processes used to create them.

ANS:	T

One of the most important and most difficult aspects of project management is defining the scope of a project. Scope refers to all the work involved in creating the products of the project and the processes used to create them.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

2.	Deliverables are only product-related, such as a piece of hardware or software.

ANS:	F

Deliverables can be product-related, such as a piece of hardware or software, or process-related, such as a planning document or meeting minutes.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

3.	Project scope management includes the processes involved in defining and controlling what is or is not included in a project.

ANS:	T

Project scope management includes the processes involved in defining and controlling what work is or is not included in a project. It ensures that the project team and stakeholders have the same understanding of what products the project will produce and what processes the project team will use to produce them.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

4.	The scope management plan can be informal and broad or formal and detailed, based on the needs of the project.

ANS:	T

The scope management plan is a subsidiary part of the project management plan. It can be informal and broad or formal and detailed, based on the needs of the project.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.189

OBJ:	LO:5-2	NAT:	BUSPROG: Technology

TOP:	Planning Scope Management	KEY:	Bloom's: Comprehension

5.	The project’s size, complexity, importance, and other factors do not affect how much effort is spent on collecting requirements for scope planning.

ANS:	F

The project’s size, complexity, importance, and other factors affect how much effort is spent on collecting requirements.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.194

OBJ:	LO:5-3	NAT:	BUSPROG: Technology	TOP:	Collecting Requirements

KEY:	Bloom's: Comprehension

6.	Information from the project charter provides a basis for further defining the project scope.

ANS:	T

The charter describes the high-level scope, time, and cost goals for the project objectives and success criteria, a general approach to accomplishing the project’s goals, and the main roles and responsibilities of important project stakeholders.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.195

OBJ:	LO: 5-4	NAT:	BUSPROG: Technology	TOP:	Defining Scope

KEY:	Bloom's: Knowledge

7.	Project scope statements must include the project boundaries, constraints, and assumptions.

ANS:	F

Project scope statements should include at least a product scope description, product user acceptance criteria, and detailed information on all project deliverables. It is also helpful to document other scope-related information, such as the project boundaries, constraints, and assumptions.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.195

OBJ:	LO: 5-4	NAT:	BUSPROG: Technology	TOP:	Defining Scope

KEY:	Bloom's: Knowledge

8.	The scope of a project is clear and specific from the start.

ANS:	F

As time progresses, the scope of a project should become more clear and specific.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.195

OBJ:	LO:5-4	NAT:	BUSPROG: Technology	TOP:	Defining Scope

KEY:	Bloom's: Comprehension

9.	Many information technology projects also require detailed functional and design specifications for developing software, which also should be referenced in the detailed scope statement.

ANS:	T

Many IT projects require detailed functional and design specifications for developing software, which also should be referenced in the detailed scope statement.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.195

OBJ:	LO: 5-4	NAT:	BUSPROG: Technology	TOP:	Defining Scope

KEY:	Bloom's: Comprehension

10.	The project scope statement should reference supporting documents, such as product specifications that will affect what products are produced or purchased, or corporate policies, which might affect how products or services are produced.

ANS:	T

The project scope statement should reference supporting documents, such as product specifications that will affect what products are created or purchased, or corporate policies, which might affect how products or services are produced.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.195

OBJ:	LO: 5-4	NAT:	BUSPROG: Technology	TOP:	Defining Scope

KEY:	Bloom's: Knowledge

11.	The project scope statement, stakeholder requirements documentation, and organizational process assets are the primary inputs for creating a WBS.

ANS:	T

The project scope management plan, scope statement, requirements documentation, enterprise environmental factors, and organizational process assets are the primary inputs for creating a WBS.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.198

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

12.	The scope baseline in a WBS consists of the requirements documentation and enterprise environmental factors.

ANS:	F

The scope baseline includes the approved project scope statement and its associated WBS and WBS dictionary.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.198

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

13.	The WBS is organized solely around project phases.

ANS:	F

A project team often organizes the WBS around project products, project phases, or the project management process groups.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.198

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

14.	A work package represents one component of the product that the project aims to deliver.

ANS:	F

A work package is a task at the lowest level of the WBS. It represents the level of work that the project manager monitors and controls.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.200

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

15.	A work package must always represent less than 80 hours of work.

ANS:	F

A work package represents the level of work that the project manager monitors and controls. If a project has a relatively short time frame and requires weekly progress reports, a work package might represent work completed in one week or less. If a project has a very long time frame and requires quarterly progress reports, a work package might represent work completed in one month or more.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.200

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

16.	The tasks in a WBS must be developed as a sequential list of steps.

ANS:	F

A concern when creating a WBS is how to organize it to provide the basis for the project schedule. You should focus on what work needs to be done and how it will be done, not when it will be done. In other words, the tasks do not have to be developed as a sequential list of steps.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.201

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

17.	The executing tasks of the WBS remain constant from project to project.

ANS:	F

The executing tasks vary the most from project to project, but many of the tasks under the other project management process groups would be similar for all projects.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.202

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

18.	Many organizations provide different guidelines and templates for developing WBSs.

ANS:	T

Many organizations provide guidelines and templates for developing WBSs, as well as examples of WBSs from past projects. Microsoft Project 2010 comes with several templates,

and more are available on Microsoft’s Web site and other sites.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.203

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

19.	Mind mapping allows people to write and even draw pictures of ideas in a nonlinear format.

ANS:	T

Instead of writing down tasks in a list or immediately trying to create a structure for tasks, mind mapping allows people to write and even draw pictures of ideas in a nonlinear format. This more visual, less structured approach to defining and then grouping tasks can unlock creativity among individuals and increase participation and morale among teams.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.205

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

20.	The format of the WBS dictionary is essentially the same for all projects.

ANS:	F

WBS dictionary is a document that provides detailed information about each WBS item. The format of the WBS dictionary can vary based on project needs.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.206

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

21.	A unit of work should appear at only one place in the WBS.

ANS:	T

A basic principle of creating a good WBS and its WBS dictionary is that a unit of work should appear at only one place in the WBS.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.207

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

22.	Scope creep if not managed well can lead to the failure of information technology projects.

ANS:	T

Even when the project scope is fairly well defined, many IT projects suffer from scope creep—the tendency for project scope to keep getting bigger and bigger. Many IT projects fail due to scope creep.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.208

OBJ:	LO:5-6	NAT:	BUSPROG: Technology	TOP:	Validating Scope

KEY:	Bloom's: Knowledge

MULTIPLE CHOICE

1.	The term ______ describes a product produced as part of a project.

| a. | variance | c. | deliverable |
| --- | --- | --- | --- |
| b. | scope | d. | work package |

ANS:	C

Thee term deliverable describes a product created as part of a project. Deliverables can be product related, such as a piece of hardware or software, or process-related, such as a planning document or meeting minutes.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

2.	Scope refers to:

| a. | each level of work that is outlined in a work breakdown structure. | c. | tasks that are decomposed into smaller tasks in a work breakdown structure. |
| --- | --- | --- | --- |
| b. | the end product created as part of a project that is delivered to the client. | d. | the work involved in creating the products and the processes used to create them. |

ANS:	D

Scope refers to all the work involved in creating the products of the project and the processes used to create them.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

3.	_____ involves defining and documenting the features and functions of the products produced during the project as well as the processes used for creating them.

| a. | Collecting requirements | c. | Controlling scope |
| --- | --- | --- | --- |
| b. | Defining scope | d. | Validating scope |

ANS:	A

Collecting requirements involves defining and documenting the features and functions of the products for the project as well as the processes used for creating them. The project team creates requirements documentation and a requirements traceability matrix as outputs of the requirements collection process.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.189

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

4.	_____ involves reviewing the project charter, requirements documents, and organizational process assets to create a scope statement, adding more information as requirements are developed and change requests are approved.

| a. | Creating scope | c. | Controlling scope |
| --- | --- | --- | --- |
| b. | Defining scope | d. | Validating scope |

ANS:	B

Defining scope involves reviewing the scope management plan, project charter, requirements documents, and organizational process assets to create a scope statement, adding more information as requirements are developed and change requests are approved.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.189

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

5.	_____ involves formalizing acceptance of the project deliverables and during this phase the key project stakeholders, such as the customer and sponsor for the project, inspect and then formally accept the deliverables.

| a. | Creating scope | c. | Controlling scope |
| --- | --- | --- | --- |
| b. | Defining scope | d. | Validating scope |

ANS:	D

Validating scope involves formalizing acceptance of the project deliverables. Key project stakeholders, such as the customer and sponsor for the project, inspect and then formally accept the deliverables during this process.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.189

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

6.	Creating the WBS is a subprocess associated with the _____ process in project scope management.

| a. | planning | c. | closing |
| --- | --- | --- | --- |
| b. | monitoring and controlling | d. | executing |

ANS:	A

Creating the WBS is a subprocess associated with the planning process of the project scope management.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.190

OBJ:	LO:5-2	NAT:	BUSPROG: Technology

TOP:	Planning Scope Management	KEY:	Bloom's: Knowledge

7.	The ______ documents how project needs will be analyzed, documented, and managed.

| a. | requirements traceability matrix | c. | WBS |
| --- | --- | --- | --- |
| b. | requirements management plan | d. | project scope statement |

ANS:	B

The requirements management plan documents how project requirements will be analyzed, documented, and managed.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.191

OBJ:	LO:5-2	NAT:	BUSPROG: Technology

TOP:	Planning Scope Management	KEY:	Bloom's: Knowledge

8.	Generating ideas by comparing specific project practices or product characteristics to those of other projects or products inside or outside the performing organization is known as _____.

| a. | variance | c. | prototyping |
| --- | --- | --- | --- |
| b. | benchmarking | d. | decomposition |

ANS:	B

Benchmarking, or generating ideas by comparing specific project practices or product characteristics to those of other projects or products inside or outside the performing organization, can be used to collect requirements.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.192

OBJ:	LO:5-3	NAT:	BUSPROG: Technology	TOP:	Collecting Requirements

KEY:	Bloom's: Knowledge

9.	A(n) _____ is a table that lists requirements, their various attributes, and the status of the requirements to ensure that all are addressed.

| a. | requirements traceability matrix | c. | state transition table |
| --- | --- | --- | --- |
| b. | Gantt chart | d. | entity-attribute-value model |

ANS:	A

A requirements traceability matrix (RTM) is a table that lists requirements, their various attributes, and the status of the requirements to ensure that all are addressed.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.194

OBJ:	LO: 5-3	NAT:	BUSPROG: Technology	TOP:	Collecting Requirements

KEY:	Bloom's: Knowledge

10.	A(n) _____ is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project.

| a. | project charter | c. | project scope statement |
| --- | --- | --- | --- |
| b. | business case | d. | work breakdown structure |

ANS:	D

After collecting requirements and defining scope, the next step in project scope management is

to create a work breakdown structure. A work breakdown structure (WBS) is a deliverable oriented grouping of the work involved in a project that defines its total scope.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.198

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

11.	The main technique used in creating a WBS is _____, which involves subdividing project deliverables into smaller pieces.

| a. | conglomeration | c. | decomposition |
| --- | --- | --- | --- |
| b. | accumulation | d. | catalyzation |

ANS:	C

The main tool or technique involved in creating a WBS is decomposition—that is, subdividing project deliverables into smaller pieces.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.198

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

12.	A(n) ____ is a task at the lowest level of the WBS.

| a. | variance | c. | deliverable |
| --- | --- | --- | --- |
| b. | objective | d. | work package |

ANS:	D

A work package is a task at the lowest level of the WBS.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.200

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

13.	The _____ should list and describe all of the deliverables required for the project.

| a. | project charter | c. | WBS |
| --- | --- | --- | --- |
| b. | scope statement | d. | Gantt chart |

ANS:	B

The scope statement should list and describe all of the deliverables required for the project. It is very important to ensure consistency between the project charter, scope statement, WBS, and Gantt chart to define the scope of the project accurately.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.202

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

14.	In the _____approach for constructing a WBS, you use a similar project’s WBS as a starting point.

| a. | top-down | c. | mind-mapping |
| --- | --- | --- | --- |
| b. | bottom-up | d. | analogy |

ANS:	D

A method for constructing a WBS is the analogy approach. In the analogy approach, you use a similar project’s WBS as a starting point.

PTS:	1	DIF:	Difficulty: Moderate		REF:	P.204

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

15.	The _____ approach for constructing a WBS involves refining the work into greater and greater levels of detail.

| a. | analogy | c. | top-down |
| --- | --- | --- | --- |
| b. | bottom-up | d. | mind mapping |

ANS:	C

To use the top-down approach, start with the largest items of the project and break them into subordinate items. This process involves refining the work into greater and greater levels of detail.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.204

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

16.	The _____ approach for constructing a WBS starts with the largest items of the project and breaks them into subordinate items.

| a. | analogy | c. | top-down |
| --- | --- | --- | --- |
| b. | bottom-up | d. | mind mapping |

ANS:	C

To use the top-down approach, start with the largest items of the project and break them

into subordinate items.The top-down approach is best suited to project managers who have vast technical insight and a big-picture perspective.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.204

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

17.	In the _____ approach, team members first identify as many specific tasks related to the project as possible and then aggregate the specific tasks and organize them into summary activities, or higher levels in the WBS.

| a. | analogy | c. | top-down |
| --- | --- | --- | --- |
| b. | bottom-up | d. | mind mapping |

ANS:	B

In the bottom-up approach, team members first identify as many specific tasks related to the project as possible. They then aggregate the specific tasks and organize them into summary activities, or higher levels in the WBS. Project managers often use the bottom-up approach for projects that represent entirely new systems or approaches to doing a job, or to help create buy-in and synergy with a project team.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.205

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

18.	The _____ technique for creating a WBS uses branches radiating from a core idea to structure thoughts and ideas instead of writing down tasks in a list or immediately trying to create a structure for tasks.

| a. | analogy | c. | top-down |
| --- | --- | --- | --- |
| b. | bottom-up | d. | mind mapping |

ANS:	D

Mind mapping is a technique that uses branches radiating from a core idea to structure thoughts and ideas.Instead of writing down tasks in a list or immediately trying to create a structure for tasks, mind mapping allows people to write and even draw pictures of ideas in a nonlinear format.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.205

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

19.	Which of the following is recommended for the creation of a good WBS?

| a. | Any WBS item should be the responsibility of all the people working on it. | c. | Each WBS item should be created assuming that the requirements are inflexible. |
| --- | --- | --- | --- |
| b. | A unit of work should appear at only one place in the WBS. | d. | The work content of a WBS item is independent of the WBS items below it. |

ANS:	B

Some basic principles apply to creating any good WBS and its WBS dictionary. Firstly, a unit of work should appear at only one place in the WBS. The work content of a WBS item is the sum of the WBS items below it.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.207

OBJ:	LO:5-5	NAT:	BUSPROG: Analytic

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

20.	Scope creep refers to:

| a. | the tendency for project scope to keep getting bigger and bigger. | c. | the approved project scope statement and its associated WBS. |
| --- | --- | --- | --- |
| b. | subdividing project deliverables into smaller pieces. | d. | a task at the lowest level of the WBS. |

ANS:	A

Scope creep refers to the tendency for project scope to keep getting bigger and bigger.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.208

OBJ:	LO:5-6	NAT:	BUSPROG: Technology	TOP:	Validating Scope

KEY:	Bloom's: Knowledge

21.	_____ involves formal acceptance of the completed project scope by the stakeholders.

| a. | Scope validation | c. | Scope control |
| --- | --- | --- | --- |
| b. | Scope planning | d. | Scope baseline |

ANS:	A

Scope validation involves formal acceptance of the completed project deliverables. This acceptance is often achieved by a customer inspection and then sign-off on key deliverables.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.209

OBJ:	LO:5-6	NAT:	BUSPROG: Technology	TOP:	Validating Scope

KEY:	Bloom's: Knowledge

22.	_____ refers to the difference between planned and actual performance.

| a. | Decomposition | c. | Scope validation |
| --- | --- | --- | --- |
| b. | Variance | d. | Scope creep |

ANS:	B

Variance is the difference between planned and actual performance.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.211

OBJ:	L:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Knowledge

23.	_____ refers to the process of developing a working replica of the system or some aspect of the system.

| a. | Prototyping | c. | Decomposition |
| --- | --- | --- | --- |
| b. | Variance | d. | Use case modeling |

ANS:	A

Prototyping involves developing a working replica of the system or some aspect of the system.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.213

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Comprehension

24.	_____ is a process for identifying and modeling business events, who initiated them, and how the system should respond to them.

| a. | Prototyping | c. | RAD |
| --- | --- | --- | --- |
| b. | JAD | d. | Use case modeling |

ANS:	D

Use case modeling is a process for identifying and modeling business events, who initiated them, and how the system should respond to them. It is an effective tool for understanding

requirements of information systems.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.213

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Knowledge

25.	 _____ uses highly organized and intensive workshops to bring together project stakeholders—the sponsor, users, business analysts, programmers, and so on—to jointly define and design information systems.

| a. | Prototyping | c. | RAD |
| --- | --- | --- | --- |
| b. | JAD | d. | Use case modeling |

ANS:	B

Joint Application Design (JAD) uses highly organized and intensive workshops to bring together project stakeholders — the sponsor, users, business analysts, programmers, and so on —to jointly define and design information systems.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.213

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Comprehension

COMPLETION

1.	_____ includes the processes involved in defining and controlling what work is or is not included in a project.

ANS:	Project scope management

PTS:	1	DIF:	Difficulty: Easy		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

2.	_____ refers to all the work involved in creating the products of the project and the processes used to create them.

ANS:	Scope

PTS:	1	DIF:	Difficulty: Easy		REF:	p.188

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

3.	The main outputs of _____are the project scope statement and updates to project documents.

ANS:	scope definition

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.189

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

4.	Creating the _____ involves subdividing the major project deliverables into smaller, more manageable components.

ANS:

WBS

work breakdown structure

work breakdown structure (WBS)

WBS (work breakdown structure)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.189

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

5.	_____ refer to “conditions or capabilities that must be met by the project or present in the product, service, or result to satisfy an agreement or other formally imposed specification.”

ANS:	Requirements

PTS:	1	DIF:	Difficulty: Easy		REF:	p.192

OBJ:	LO:5-2	NAT:	BUSPROG: Technology

TOP:	Planning Scope Management	KEY:	Bloom's: Knowledge

6.	A(n) _____  is a table that lists requirements, their various attributes, and the status of the requirements to ensure that all are addressed.

ANS:

requirements traceability matrix

requirements traceability matrix (RTM)

RTM

PTS:	1	DIF:	Difficulty: Easy		REF:	p.194

OBJ:	LO:5-3	NAT:	BUSPROG: Technology	TOP:	Collecting Requirements

KEY:	Bloom's: Knowledge

7.	The main outputs of scope definition are the _____ and project document updates.

ANS:	project scope statement

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.195

OBJ:	LO:5-4	NAT:	BUSPROG: Technology	TOP:	Defining Scope

KEY:	Bloom's: Knowledge

8.	A(n) _____ is a deliverable-oriented grouping of the work involved in a project that defines its total scope.

ANS:

WBS

work breakdown structure

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.198

OBJ:	LO:5-4	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

9.	Subdividing the project deliverables into smaller pieces is known as _____.

ANS:	decomposition

PTS:	1	DIF:	Difficulty: Easy		REF:	p.198

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

10.	The _____ includes the approved project scope statement and its associated WBS and WBS dictionary.

ANS:	scope baseline

PTS:	1	DIF:	Difficulty: Easy		REF:	p.198

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

11.	Tasks in a WBS that are decomposed into smaller tasks are called _____ tasks.

ANS:	summary

PTS:	1	DIF:	Difficulty: Easy		REF:	p.199

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

12.	PMI uses the term “_____” to describe each level of work in the WBS.

ANS:	task

PTS:	1	DIF:	Difficulty: Easy		REF:	p.200

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

13.	A work package is a task at the _____ level of the WBS.

ANS:	lowest

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.200

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

14.	Some organizations prescribe the form and content for WBSs for particular projects. These are known as _____.

ANS:	guidelines

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.203

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

15.	In the _____ approach to creating a WBS, team members first identify as many specific tasks related to the project as possible.

ANS:	bottom-up

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.204

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Comprehension

16.	_____ is a technique that uses branches radiating out from a core idea to structure thoughts and ideas when creating a WBS.

ANS:	Mind mapping

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.205

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

17.	A(n) _____ is a document that describes detailed information about each WBS item.

ANS:	WBS dictionary

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.206

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

18.	_____ is the tendency for project scope to keep getting bigger and bigger.

ANS:	Scope creep

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.208

OBJ:	LO: 5-6	NAT:	BUSPROG: Technology	TOP:	Validating Scope

KEY:	Bloom's: Knowledge

19.	The main tool for performing scope validation is _____ and group decision making techniques.

ANS:	inspection

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.209

OBJ:	LO: 5-6	NAT:	BUSPROG: Technology	TOP:	Validating Scope

KEY:	Bloom's: Knowledge

20.	_____ involves controlling changes to the project scope while keeping project goals and business strategy in mind.

ANS:	Scope control

PTS:	1	DIF:	Difficulty: Easy		REF:	p.210

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Knowledge

21.	_____ is the difference between planned and actual performance.

ANS:	Variance

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.211

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Comprehension

22.	_____ involves developing a working replica of the system or some aspect of the system.

ANS:	Prototyping

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.213

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Comprehension

23.	_____ is a process for identifying and modeling business events, who initiated them, and how the system should respond to them.

ANS:	Use case modeling

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.213

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Comprehension

ESSAY

1.	List and briefly describe the six main processes involved in project scope management.

ANS:

1. Planning scope management involves determining how the project’s scope and requirements will be managed. The project team works with appropriate stakeholders to create a scope management plan and requirements management plan.

188

2. Collecting requirements involves defining and documenting the features and functions of the products produced during the project as well as the processes used for creating them. The project team creates stakeholder requirements documentation, a requirements management plan, and a requirements traceability matrix as outputs of the requirements collection process.

3. Defining scope involves reviewing the project charter, requirements documents, and organizational process assets to create a scope statement, adding more information as requirements are developed and change requests are approved. The main outputs of scope definition are the project scope statement and updates to project documents.

4.Creating the WBS involves subdividing the major project deliverables into smaller, more manageable components. The main outputs include a work breakdown structure, a WBS dictionary, a scope baseline, and updates to project documents.

5. Verifying scope involves formalizing acceptance of the project deliverables. Key project stakeholders, such as the customer and sponsor for the project, inspect and then formally accept the deliverables during this process. If the deliverables are not acceptable, the customer or sponsor usually requests changes. The main outputs of this process, therefore, are accepted deliverables, change requests, work performance information, and updates to project documents.

6. Controlling scope involves controlling changes to project scope throughout the life of the project—a challenge on many information technology projects. Scope changes often influence the team’s ability to meet project time and cost goals, so project managers must carefully weigh the costs and benefits of scope changes. The main outputs of this process are work performance information, change requests, and updates to the project management plan, project documents, and organizational process assets.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.188-189

OBJ:	LO:5-1	NAT:	BUSPROG: Technology

TOP:	What Is Project Scope Management?			KEY:	Bloom's: Knowledge

2.	What is a work breakdown structure? What are the inputs and tools used for creating one?

ANS:

A work breakdown structure (WBS) is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project. Because most projects involve many people and many different deliverables, it is important to organize and divide the work into logical parts based on how the work will be performed. The WBS is a foundation document in project management because it provides the basis for planning and managing project schedules, costs, resources, and changes. Since the WBS defines the total scope of the project, some project management experts believe that work should not be done on a project if it is not included in the WBS. Therefore, it is crucial to develop a good WBS.

The project scope statement, stakeholder requirements documentation, and organizational process assets are the primary inputs for creating a WBS. The main tool or technique is decomposition, that is, subdividing project deliverables into smaller pieces. The outputs of the process of creating the WBS are the WBS itself, the WBS dictionary, a scope baseline, and project document updates.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.198

OBJ:	LO: 5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

3.	List and briefly describe five approaches for creating work breakdown structures.

ANS:

Using Guidelines

If guidelines for developing a WBS exist, it is very important to follow them. Some organizations—the U.S. Department of Defense (DOD) for example—prescribe the form and content for WBSs for particular projects.

Many organizations provide guidelines and templates for developing WBSs, as well as examples of WBSs from past projects. At the request of many of its members, the Project Management Institute recently developed a WBS Practice Standard to provide guidance for developing and applying the WBS to project management.

Project managers and their teams should review appropriate information to develop their unique project WBSs more efficiently.

The Analogy Approach

In the analogy approach, you use a similar project’s WBS as a starting point. Some organizations keep a repository of WBSs and other project documentation on file to assist people working on projects. Viewing examples of other similar projects’ WBSs allows you to understand different ways to create a WBS.

The Top-down and Bottom-up Approaches

Most project managers consider the top-down approach of WBS construction to be conventional. To use the top-down approach, start with the largest items of the project and break them into their subordinate items. This process involves refining the work into greater and greater levels of detail. After finishing the process, all resources should be assigned at the work package level. The top-down approach is best suited to project managers who have vast technical insight and a big-picture perspective.

In the bottom-up approach, team members first identify as many specific tasks related to the project as possible. They then aggregate the specific tasks and organize them into summary activities, or higher levels in the WBS. The bottom-up approach can be very time-consuming, but it can also be a very effective way to create a WBS. Project managers often use the bottom-up approach for projects that represent entirely new systems or approaches to doing a job, or to help create buy-in and synergy with a project team.

Mind Mapping

Mind mapping is a technique that uses branches radiating out from a core idea to structure thoughts and ideas. Instead of writing tasks down in a list or immediately trying to create a structure for tasks, mind mapping allows people to write and even draw pictures of ideas in a nonlinear format. This more visual, less structured approach to defining and then grouping tasks can unlock creativity among individuals and increase participation and morale among teams.

After discovering WBS items and structure using the mind-mapping technique, you could then translate the information into chart or tabular form. Mind mapping can be used for developing WBSs using the top-down or bottom-up approach.

PTS:	1	DIF:	Difficulty: Challenging	REF:	p.203-206

OBJ:	LO:5-5	NAT:	BUSPROG: Technology

TOP:	Creating The Work Breakdown Structure		KEY:	Bloom's: Knowledge

4.	Describe the process of scope verification.

ANS:

Scope verification involves formal acceptance of the completed project scope by the stakeholders. This acceptance is often achieved by a customer inspection and then sign-off on key deliverables. To receive formal acceptance of the project scope, the project team must develop clear documentation of the project’s products and procedures to evaluate if they were completed correctly and satisfactorily. To minimize scope changes, it is crucial to do a good job of verifying project scope.

The scope management plan, scope baseline, requirements documentation, requirements traceability matrix, validated deliverables, and work performance data are the main inputs for scope validation. The main tools for performing scope validation are inspection and group decision-making techniques. The customer, sponsor, or user inspects the work after it is delivered and decides if it meets requirements. The main outputs of scope validation are accepted deliverables, change requests, work performance information, and project documents updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.209-210

OBJ:	LO: 5-6	NAT:	BUSPROG: Technology	TOP:	Validating Scope

KEY:	Bloom's: Knowledge | Bloom's: Knowledge

5.	What are some of the suggestions for improving the requirements process?

ANS:

1. Develop and follow a requirements management process that includes procedures for initial requirements determination.

2. Employ techniques such as prototyping, use case modeling, and Joint Application Design to understand user requirements thoroughly. Prototyping involves developing a working replica of the system or some aspect of the system. These working replicas may be throwaways or an incremental component of the deliverable system. Prototyping is an effective tool for gaining an understanding of requirements, determining the feasibility of requirements, and resolving user interface uncertainties. Use case modeling is a process for identifying and modeling business events, who initiated them, and how the system should respond to them. It is an effective tool for understanding requirements for information systems. Joint Application Design (JAD) uses highly organized and intensive workshops to bring together project stakeholders—the sponsor, users, business analysts, programmers, and so on—to jointly define and design information systems. These techniques also help users become more active in defining system requirements.

3. Put all requirements in writing and keep them current and readily available. Several tools are available to automate this function. For example, a type of software called a requirements management tool aids in capturing and maintaining requirements information, provides immediate access to the information, and assists in establishing necessary relationships between requirements and information created by other tools.

4. Create a requirements management database for documenting and controlling requirements. Computer Aided Software Engineering (CASE) tools or other technologies can assist in maintaining a repository for project data. A CASE tool’s database can also be used to document and control requirements.

5. Provide adequate testing to verify that the project’s products perform as expected. Conduct testing throughout the project life cycle.

6. Use a process for reviewing requested requirements changes from a systems perspective.

7. Emphasize completion dates.

8. Allocate resources specifically for handling change requests.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.213-214

OBJ:	LO:5-7	NAT:	BUSPROG: Technology	TOP:	Controlling Scope

KEY:	Bloom's: Comprehension