Chapter 7: Project Cost Management

TRUE/FALSE

1.	Overrun is the additional percentage amount by which estimates exceed actual costs.

ANS:	F

Overrun is the additional percentage or dollar amount by which actual costs exceed estimates.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.272

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

2.	The primary output of the planning cost management process is a change request.

ANS:	F

The main output of the planning cost management process process is a cost management plan. Planning cost management involves determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.274

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

3.	IT project managers must be able to present and discuss project information both in financial and technical terms.

ANS:	T

Most members of a company’s executive board have a better understanding of financial terms than IT terms, and are more interested in finance. Therefore, IT project managers need to be able to present and discuss project information both in financial terms and technical terms.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.276

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

4.	Project managers must conduct cash flow analysis to determine net present value.

ANS:	T

Cash flow analysis is a method of determining the estimated annual costs and benefits for a project and the resulting annual cash flow. Project managers must conduct cash flow analysis to determine net present value.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.277

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

5.	Intangible costs can be easily measured in monetary terms.

ANS:	F

Intangible costs or benefits are difficult to measure in monetary terms. Conversely, tangible costs or benefits can easily be measured in dollars.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

6.	When deciding what projects to invest in or continue, one should include sunk costs.

ANS:	F

Sunk cost is money that has been spent in the past. When deciding what projects to invest in or continue, one should not include sunk costs.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

7.	It is important for project managers to focus on indirect costs because they can be easily controlled.

ANS:	F

Direct costs can be directly related to creating the products and services of the project. Project managers should focus on direct costs because they can be controlled.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

8.	If an important supplier goes out of business, management reserves can be set aside to cover the resulting costs.

ANS:	T

Management reserves allow for future situations that are unpredictable. For example, if a project manager gets sick for two weeks or an important supplier goes out of business, management reserves could be set aside to cover the resulting costs.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.279

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

9.	Contingency reserves are also known as unknown unknowns.

ANS:	F

Contingency reserves allow for future situations that may be partially planned for. They are sometimes called known unknowns.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.279

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

10.	A cost management plan can include organizational procedures links, control thresholds, and process descriptions.

ANS:	T

In general, a cost management plan includes level of accuracy, organizational procedures links, process descriptions, control thresholds, and rules of performance measurement, among others.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.279

OBJ:	LO: 7-3	NAT:	BUSPROG: Technology	TOP:	Planning Cost Management

KEY:	Bloom's: Knowledge

11.	A budgetary estimate is the most accurate of the three types of estimates.

ANS:	F

A definitive estimate provides an accurate estimate of project costs. It provides details for purchases and estimates actual costs.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

12.	Budgetary estimates are made even before a project is officially started.

ANS:	F

Budgetary estimates are made one to two years prior to project completion.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

13.	Definitive estimates are made one year or less prior to project completion.

ANS:	T

Definitive estimates are made one year or less prior to project completion. They provide an accurate estimate of project costs.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.281

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

14.	Estimates should become more accurate as time progresses.

ANS:	T

Estimates are usually done at various stages of a project and should become more accurate as time progresses.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.281

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

15.	Supporting details for an estimate include the ground rules and assumptions used in creating the estimate.

ANS:	T

In addition to creating cost estimates for the entire project and activity cost estimates, it is also important to provide supporting details for the estimates and updates to project documents. The supporting details include the ground rules and assumptions used in creating the estimate, a description of the project used as a basis for the estimate, and details on the cost estimation tools and techniques used to create the estimate.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.281

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

16.	Analogous estimates are called activity-based costing.

ANS:	F

Analogous estimates are also called top-down estimates. Such estimates use the actual cost of a previous, similar project as the basis for estimating the cost of the current project.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

17.	Analogous estimates are the most accurate technique to estimate costs.

ANS:	F

Analogous estimates requires a good deal of expert judgment and is generally less costly than other techniques. However, it is also less accurate.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

18.	In a bottom-up estimate, the size of the individual work items is one of the factors that drives the accuracy of the estimates.

ANS:	T

The size of the individual work items and the experience of the estimators drive the accuracy of the estimates. Using smaller work items increases the accuracy of the cost estimate because the people assigned to do the work develop the cost estimate instead of someone unfamiliar with the work.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

19.	Parametric models are reliable when the models are flexible in terms of the project’s size.

ANS:	T

Parametric models are most reliable when the historical information used to create the model is accurate, the parameters are readily quantifiable, and the model is flexible in terms of the project’s size.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.283

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

20.	One of the reasons why project cost estimates are inaccurate is because human beings are biased toward underestimation.

ANS:	T

One of the reasons why project cost estimates are very inaccurate is because human beings are biased toward underestimation. It is thus important for project managers and top management to review estimates and ask important questions to make sure the estimates are not biased.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.284

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

21.	It is important for project managers to understand that every cost estimate is unique.

ANS:	T

Every cost estimate is unique, just as every project is unique.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.284

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

22.	Determining the budget involves allocating the project cost estimate to individual work items over time.

ANS:	T

Determining the budget involves allocating the project cost estimate to individual material resources or work items over time. These material resources or work items are based on

the activities in the work breakdown structure for the project.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.289

OBJ:	LO: 7-5	NAT:	BUSPROG: Technology	TOP:	Determining the Budget

KEY:	Bloom's: Knowledge

23.	The project management plan and project funding requirements are inputs of the process of controlling costs.

ANS:	T

The project management plan, project funding requirements, work performance data, and organizational process assets are inputs for controlling costs.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.289

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

24.	The formulas for variances and indexes start with EV, the earned value.

ANS:	T

The formulas for variances and indexes start with EV, the earned value. Variances are calculated by subtracting the actual cost or planned value from EV, and indexes are calculated by dividing EV by the actual cost or planned value.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

25.	If cost variance is a positive number, it means that performing the work costs more than planned.

ANS:	F

Cost variance (CV) is the earned value minus the actual cost. If cost variance is a negative number, it means that performing the work costs more than planned. If cost variance is a positive number, performing the work costs less than planned.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

26.	A negative schedule variance means that it took lesser than planned to perform the work.

ANS:	F

A negative schedule variance means that it took longer than planned to perform the work, and a positive schedule variance means that the work took less time than planned to perform.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

27.	If the cost performance index (CPI) is less than 100 percent, the project is under budget.

ANS:	F

If the CPI is less than one or less than 100 percent, the project is over budget. On the other hand, if the CPI is greater than one or more than 100 percent, the project is under budget.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

28.	A schedule performance index of one means that the project is on schedule.

ANS:	T

The schedule performance index (SPI) is the ratio of earned value to planned value; it can be used to estimate the projected time to complete the project. A schedule performance index of one means the project is on schedule.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.294

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

29.	In an earned value chart, when the actual cost line is right on or above the earned value line, it indicates that costs are less than planned.

ANS:	F

Viewing earned value information in chart form helps in visualizing how a project is performing. If the actual cost line is always on or above the earned value line, it indicates that costs are equal to or more than planned.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.295

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

30.	Spreadsheets are a common tool for cost estimating, cost budgeting, and cost control.

ANS:	T

Most organizations use software to assist in various activities related to project cost management. Spreadsheets are a common tool for cost estimating, cost budgeting, and cost control.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.299

OBJ:	LO: 7-7	NAT:	BUSPROG: Technology

TOP:	Using Project Management Software to assist In Project Cost Management

KEY:	Bloom's: Knowledge

MULTIPLE CHOICE

1.	_____ includes the processes required to ensure that a project team completes a project within an approved budget.

| a. | Project scope management | c. | Project time management |
| --- | --- | --- | --- |
| b. | Project quality management | d. | Project cost management |

ANS:	D

Project cost management includes the processes required to ensure that a project team completes a project within an approved budget. Project managers must make sure their projects are well defined, have accurate time and cost estimates, and have a realistic budget that they were involved in approving.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.274

OBJ:	LO: 7-1	NAT:	BUSPROG: Analytic

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

2.	Which of the following involves developing an approximation of the costs of resources needed to complete a project?

| a. | Determining the budget | c. | Controlling costs |
| --- | --- | --- | --- |
| b. | Finalising the cost baseline | d. | Estimating costs |

ANS:	D

Estimating costs involves developing an approximation or estimate of the costs of the resources needed to complete a project. The main outputs of the cost estimating process are activity cost estimates, basis of estimates, and project documents updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.274

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Comprehension

3.	_____ involves allocating the overall cost estimate to individual work items to establish a baseline for measuring performance.

| a. | Determining the budget | c. | Controlling costs |
| --- | --- | --- | --- |
| b. | Finalising policies for project costs | d. | Estimating costs |

ANS:	A

Determining the budget involves allocating the overall cost estimate to individual work items to establish a baseline for measuring performance.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.275

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Comprehension

4.	One of the main outputs of the _____ process is a cost baseline.

| a. | cost controlling | c. | cost budgeting |
| --- | --- | --- | --- |
| b. | cost estimating | d. | cost planning |

ANS:	C

Determining the budget involves allocating the overall cost estimate to individual work items to establish a baseline for measuring performance. The main outputs of the cost budgeting process are a cost baseline, project funding requirements, and project documents updates.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.275

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

5.	The process of controlling costs primarily involves:

| a. | determining the policies for project costs. | c. | finalising the procedures for project costs. |
| --- | --- | --- | --- |
| b. | managing changes to the project budget. | d. | determining a basis for estimates. |

ANS:	B

Controlling costs involves controlling changes to the project budget. The main outputs of the cost control process are work performance information, cost forecasts, change requests, project management plan updates, project documents updates, and organizational process assets updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.275

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Comprehension

6.	Work performance information and cost forecasts are main outputs of the _____ process.

| a. | cost budgeting | c. | cost control |
| --- | --- | --- | --- |
| b. | cost estimating | d. | cost pricing |

ANS:	C

Controlling costs involves controlling changes to the project budget. The main outputs of the cost control process are work performance information, cost forecasts, change requests, project management plan updates, project documents updates, and organizational process assets updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.275

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Comprehension

7.	Profits may be defined as:

| a. | expenses plus net income. | c. | revenues plus expenses. |
| --- | --- | --- | --- |
| b. | costs plus revenues. | d. | revenues minus expenditures. |

ANS:	D

Profits are revenues minus expenditures. To increase profits, a company can increase revenues, decrease expenses, or try to do both.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.276

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

8.	_____ helps develop an accurate projection of a project’s financial expenses and benefits.

| a. | Critical path analysis | c. | Life cycle costing |
| --- | --- | --- | --- |
| b. | Fast tracking | d. | Crashing |

ANS:	C

Life cycle costing helps develop an accurate projection of a project’s financial costs and benefits. It allows one to see a big-picture view of the cost of a project throughout its life cycle.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.276

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

9.	_____ is a method for determining the estimated annual costs and benefits for a project.

| a. | Critical path analysis | c. | Present value analysis |
| --- | --- | --- | --- |
| b. | Cash flow analysis | d. | Requirements analysis |

ANS:	B

Cash flow analysis is a method for determining the estimated annual costs and benefits for a project and the resulting annual cash flow. Project managers must conduct cash flow analysis to determine net present value.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.277

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

10.	Which of the following is true of tangible costs?

| a. | They cannot be calculated in monetary terms. | c. | They are difficult to quantify. |
| --- | --- | --- | --- |
| b. | They can be easily measured. | d. | Their examples include goodwill and prestige. |

ANS:	B

Tangible and intangible costs and benefits are categories for determining how well an organization can define the estimated costs and benefits for a project. Tangible costs or benefits can easily be measured in dollars.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

11.	_____ are those costs that are difficult to measure in monetary terms.

| a. | Intangible costs | c. | Tangible costs |
| --- | --- | --- | --- |
| b. | Direct costs | d. | Fixed costs |

ANS:	A

Intangible costs or benefits are difficult to measure in monetary terms.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

12.	Newtech Inc. hires John for the position of a software programmer to work on their new project. Salary paid to John by Newtech Inc. would be an example of _____ costs.

| a. | direct | c. | sunk |
| --- | --- | --- | --- |
| b. | indirect | d. | intangible |

ANS:	A

Direct costs can be directly related to creating the products and services of a project.

For instance, direct costs include the salaries of people working full time on a project.

PTS:	1	DIF:	Difficulty: Challenging	REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Reflective Thinking

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Application

13.	Indirect costs are:

| a. | directly related to performing the project. | c. | those that can be easily controlled by managers. |
| --- | --- | --- | --- |
| b. | those that cannot be allocated to projects. | d. | not directly related to the products or services of a project. |

ANS:	D

Indirect costs are not directly related to the products or services of the project, but are indirectly related to performing the project.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

14.	Soles is a footwear company which has recently set up its store in Ambrosia. To manufacture its products, Soles incurs a range of different costs. Which of the following would be an example of an indirect cost?

| a. | Cost of machines to produce shoes | c. | Electricity used to run its factories |
| --- | --- | --- | --- |
| b. | Salary paid to factory workers | d. | Cost of leather used to manufacture shoes |

ANS:	C

Indirect costs are not directly related to the products or services of the project, but are indirectly related to performing the project. For example, indirect costs would include the cost of electricity, paper towels, and other necessities in a large building that houses 1,000 employees who work on many projects.

PTS:	1	DIF:	Difficulty: Challenging	REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Reflective Thinking

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Application

15.	Good Earth, a company manufacturing packaged food products, sets up its stores in Baltonia. However, a year later, the company closes the store down due to high operating costs. In such a scenario, the money spent in paying for the rent of the store in Baltonia would be an example of _____ costs.

| a. | recurring | c. | sunk |
| --- | --- | --- | --- |
| b. | direct | d. | intangible |

ANS:	C

Sunk cost is money that has been spent in the past. When deciding what projects to invest in or continue, one should not include sunk costs.

PTS:	1	DIF:	Difficulty: Challenging	REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Reflective Thinking

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Application

16.	Which of the following is true of contingency reserves?

| a. | They allow for future situations that can be partially planned for. | c. | They are not included in a cost baseline. |
| --- | --- | --- | --- |
| b. | They are also known as unknown unknowns. | d. | They allow for dollar amounts to be used to cover existing, fixed costs. |

ANS:	A

Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.279

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

17.	Which of the following reserves allows for future situations that are unpredictable?

| a. | Contingency reserves | c. | Known unknowns |
| --- | --- | --- | --- |
| b. | Management reserves | d. | Cost baseline reserves |

ANS:	B

Management reserves allow for future situations that are unpredictable. They are sometimes called unknown unknowns.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.279

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

18.	The first step in project cost management is:

| a. | to allocate project cost estimates to individual material resources. | c. | to control project costs and monitor cost performance. |
| --- | --- | --- | --- |
| b. | to plan how costs will be managed. | d. | to develop several estimates of costs for different types of resources. |

ANS:	B

The first step in project cost management is planning how the costs will be managed throughout the life of the project. The project manager and other stakeholders use expert judgment, analytical techniques, and meetings to produce the cost management plan.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.279

OBJ:	LO: 7-3	NAT:	BUSPROG: Analytic		TOP:	Planning Cost Management

KEY:	Bloom's: Knowledge

19.	Which of the following is true of a rough order of magnitude estimate?

| a. | It is used to allocate money into an organization’s budget. | c. | Its timeframe is always less than a year prior to project completion. |
| --- | --- | --- | --- |
| b. | It provides an estimate of what a project will cost. | d. | It is a type of estimate that is done in the final stages of a project. |

ANS:	B

A rough order of magnitude (ROM) estimate provides an estimate of what a project will cost. This type of estimate is done very early in a project or even before a project is officially started.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

20.	A rough order of magnitude estimate can be referred to as a _____ estimate.

| a. | definitive | c. | final |
| --- | --- | --- | --- |
| b. | budgetary | d. | ballpark |

ANS:	D

A rough order of magnitude (ROM) estimate provides an estimate of what a project will cost. A ROM estimate can also be referred to as a ballpark estimate, a guesstimate, a swag, or a broad gauge.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

21.	A cost estimation tool which is used to allocate money into an organization’s budget is known as a _____ estimate.

| a. | budgetary | c. | rough order of magnitude |
| --- | --- | --- | --- |
| b. | definitive | d. | ballpark |

ANS:	A

A budgetary estimate is used to allocate money into an organization’s budget. Budgetary estimates are made one to two years prior to project completion.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

22.	A _____ estimate is used for making many purchasing decisions for which accurate estimates are required and for estimating final project costs.

| a. | budgetary | c. | rough order of magnitude |
| --- | --- | --- | --- |
| b. | definitive | d. | final |

ANS:	B

A definitive estimate provides an accurate estimate of project costs. Definitive estimates are used for making many purchasing decisions for which accurate estimates are required and for estimating final project costs.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

23.	Which of the following types of estimate use the actual cost of a previous, similar project as the basis for estimating the cost of the current project?

| a. | Definitive estimates | c. | Bottom-up estimates |
| --- | --- | --- | --- |
| b. | Parametric estimates | d. | Analogous estimates |

ANS:	D

Analogous estimates use the actual cost of a previous, similar project as the basis for estimating the cost of the current project. This technique requires a good deal of expert judgment and is generally less costly than other techniques, but it is also less accurate.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

24.	Analogous estimates are also known as _____ estimates.

| a. | bottom-up | c. | parametric |
| --- | --- | --- | --- |
| b. | top-down | d. | budgetary |

ANS:	B

Analogous estimates use the actual cost of a previous, similar project as the basis for estimating the cost of the current project. They are also called top-down estimates.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

25.	Which of the following is true of analogous estimates?

| a. | Their main disadvantage is that they cost more than other techniques. | c. | They are most reliable when previous projects are similar in fact with current projects. |
| --- | --- | --- | --- |
| b. | They are the only technique which do not require expert judgement. | d. | They use project characteristics in a mathematical model to estimate project costs. |

ANS:	C

Analogous estimates use the actual cost of a previous, similar project as the basis for estimating the cost of the current project. They are most reliable when the previous projects are similar in fact, not just in appearance.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

26.	A cost estimation tool which involves estimating individual work items or activities and summing them to get a project total is known as a(n) _____ estimate.

| a. | budgetary | c. | bottom-up |
| --- | --- | --- | --- |
| b. | parametric | d. | analogous |

ANS:	C

Bottom-up estimates involve estimating the costs of individual work items or activities and summing them to get a project total. This approach is sometimes referred to as activity-based costing.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.282

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

27.	Which of the following is true of bottom-up estimates?

| a. | They are based on the actual cost of a previous, similar project. | c. | They are most accurate when they involve large, extensive work items. |
| --- | --- | --- | --- |
| b. | They are also known as parametric estimating. | d. | They are time-intensive and expensive to develop. |

ANS:	D

Bottom-up estimates involve estimating the costs of individual work items or activities and summing them to get a project total. The drawback with bottom-up estimates is that they are usually time-intensive and therefore expensive to develop.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.283

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

28.	_____ uses project characteristics in a mathematical model to estimate project costs.

| a. | Rough order of magnitude estimating | c. | Bottom-up estimating |
| --- | --- | --- | --- |
| b. | Parametric estimating | d. | Analogous estimating |

ANS:	B

Parametric estimating uses project characteristics (parameters) in a mathematical model to estimate project costs.

PTS:	1	DIF:	Difficulty: Knowledge	REF:	p.283

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

29.	Which of the following is most likely to be a reason for inaccuracies in information technology cost estimates?

| a. | Estimates take a long time to be worked out. | c. | Human beings are biased toward overestimation. |
| --- | --- | --- | --- |
| b. | People lack estimating experience. | d. | Only software development provides the scope for estimates to be accurate. |

ANS:	B

The people who develop software cost estimates often do not have much experience with cost estimation, especially for large projects. They also do not have enough accurate, reliable project data on which to base estimates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.284

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

30.	If the cost estimate for a project is a basis for contract awards and performance reporting, it should be a(n) _____ estimate and as accurate as possible.

| a. | budgetary | c. | rough order of magnitude |
| --- | --- | --- | --- |
| b. | definitive | d. | analogous |

ANS:	B

If the cost estimate for a project is a basis for contract awards and performance reporting, it should be a definitive estimate and as accurate as possible.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.284

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

31.	The main goal of the _____ process is to produce a cost baseline for measuring project performance and project funding requirements.

| a. | cost budgeting | c. | cost controlling |
| --- | --- | --- | --- |
| b. | cost planning | d. | cost estimating |

ANS:	A

The main goal of the cost budgeting process is to produce a cost baseline for measuring project performance and to determine project funding requirements. Determining the budget involves allocating the project cost estimate to individual material resources or work items over time.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.289

OBJ:	LO: 7-5	NAT:	BUSPROG: Analytic		TOP:	Determining the Budget

KEY:	Bloom's: Comprehension

32.	Which of the following is an output of the process of controlling costs?

| a. | Cost forecasts | c. | Basis of estimates |
| --- | --- | --- | --- |
| b. | Project funding requirements | d. | Scope baselines |

ANS:	A

Outputs of the process of controlling costs are work performance information, cost forecasts, change requests, project management plan updates, project documents updates, and organizational process asset updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.289

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

33.	Which of the following is an input of the process of controlling costs?

| a. | Cost forecasts | c. | Change requests |
| --- | --- | --- | --- |
| b. | Work performance data | d. | Scope baseline |

ANS:	B

The project management plan, project funding requirements, work performance data, and organizational process assets are inputs for controlling costs.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.291

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

34.	The budget is one of the three values of earned value management and is also known as _____.

| a. | earned value | c. | indirect cost |
| --- | --- | --- | --- |
| b. | actual cost | d. | planned value |

ANS:	D

The planned value (PV), also called the budget, is the portion of the approved total cost estimate planned to be spent on an activity during a given period.

PTS:	1	DIF:	Difficulty: Easy		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

35.	Which of the following is true of earned value?

| a. | It is the actual cost plus the planned cost. | c. | It is an estimate of the value of the physical work actually completed. |
| --- | --- | --- | --- |
| b. | It is based solely on the total cost estimate to be spent on an activity. | d. | It is also known as the planned value. |

ANS:	C

The earned value (EV) is an estimate of the value of the physical work actually completed. EV is based on the original planned costs for the project or activity and the rate at which the team is completing work on the project or activity to date.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

36.	Variances are calculated by subtracting the actual cost from _____.

| a. | earned value | c. | planned value |
| --- | --- | --- | --- |
| b. | schedule variance | d. | rate of performance |

ANS:	A

Variances are calculated by subtracting the actual cost or planned value from EV or earned value, and indexes are calculated by dividing EV by the actual cost or planned value.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Analytic		TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

37.	Cost variance is:

| a. | the planned value plus actual costs. | c. | the rate of performance minus earned value. |
| --- | --- | --- | --- |
| b. | the earned value minus the actual cost. | d. | the planned value minus the rate of performance. |

ANS:	B

Cost variance (CV) is the earned value minus the actual cost. If cost variance is a negative number, it means that performing the work costs more than planned. If cost variance is a positive number, performing the work costs less than planned.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Analytic		TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

38.	Schedule variance is:

| a. | the earned value minus the planned value. | c. | the planned value plus the earned value. |
| --- | --- | --- | --- |
| b. | the earned value minus the actual cost. | d. | the planned value plus the rate of performance. |

ANS:	A

Schedule variance (SV) is the earned value minus the planned value. A negative schedule variance means that it took longer than planned to perform the work, and a positive schedule variance means that the work took less time than planned to perform.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Analytic		TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

39.	The cost performance index (CPI):

| a. | indicates that a project is under budget if CPI is less than one. | c. | indicates that the planned and actual costs are equal if CPI is more than one. |
| --- | --- | --- | --- |
| b. | can be used to estimate the projected cost of completing the project. | d. | is the ratio of earned value to planned value. |

ANS:	B

The cost performance index (CPI) is the ratio of earned value to actual cost; it can be used to estimate the projected cost of completing the project.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.293

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

40.	Which of the following is true of the schedule performance index (SPI)?

| a. | It can be used to estimate the projected time to complete the project. | c. | It means that a project is ahead of schedule if SPI is lesser than one or hundred percent. |
| --- | --- | --- | --- |
| b. | It means that a project is behind schedule if an SPI is greater than one. | d. | It is the ratio of planned value to actual costs. |

ANS:	A

The schedule performance index (SPI) is the ratio of earned value to planned value; it can be used to estimate the projected time to complete the project.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.294

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

COMPLETION

1.	The additional percentage or dollar amount by which actual costs exceed estimates is known as a(n) _____.

ANS:	overrun

PTS:	1	DIF:	Difficulty: Easy		REF:	p.272

OBJ:	LO: 7-1	NAT:	BUSPROG: Analytic

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

2.	The main output of the planning cost management process is a(n) _____.

ANS:	cost management plan

PTS:	1	DIF:	Difficulty: Easy		REF:	p.274

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

3.	The main outputs of the _____ process are activity cost estimates, basis of estimates, and project document updates.

ANS:	cost estimating

PTS:	1	DIF:	Difficulty: Easy		REF:	p.274

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

4.	The main outputs of the _____ process are a cost performance baseline, project funding requirements, and project document updates.

ANS:	cost budgeting

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.275

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Knowledge

5.	_____ are revenues minus expenditures.

ANS:	Profits

PTS:	1	DIF:	Difficulty: Easy		REF:	p.276

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

6.	_____ costing helps to see a big-picture view of the cost of a project throughout its life cycle.

ANS:	Life cycle

PTS:	1	DIF:	Difficulty: Easy		REF:	p.276

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

7.	_____ costing considers the total cost of ownership, or development plus support costs, for a project.

ANS:	Life cycle

PTS:	1	DIF:	Difficulty: Easy		REF:	p.276

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

8.	Project managers must conduct cash flow analysis to determine _____.

ANS:	net present value

PTS:	1	DIF:	Difficulty: Easy		REF:	p.277

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Knowledge

9.	The _____ theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced.

ANS:	learning curve

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Technology

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

10.	Project costs, like project schedules, grow out of the basic documents that initiate a project, like the _____.

ANS:	project charter

PTS:	1	DIF:	Difficulty: Easy		REF:	p.279

OBJ:	LO: 7-3	NAT:	BUSPROG: Technology	TOP:	Planning Cost Management

KEY:	Bloom's: Knowledge

11.	A(n) _____ estimate is done very early in a project or even before a project is officially started.

ANS:	rough order of magnitude (ROM)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

12.	The timeframe for a(n) _____ estimate is often three or more years prior to project completion.

ANS:	rough order of magnitude (ROM)

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.280

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

13.	In practice, many people find that using a combination or hybrid approach involving analogous, bottom up, and/or parametric modeling provides the best _____.

ANS:	cost estimates

PTS:	1	DIF:	Difficulty: Easy		REF:	p.283

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Knowledge

14.	Project cost estimates are allocated to work items which are based on the activities in the _____ for the project.

ANS:	work breakdown structure

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.288

OBJ:	LO: 7-5	NAT:	BUSPROG: Technology	TOP:	Determining the Budget

KEY:	Bloom's: Comprehension

15.	A(n) _____ is a time-phased budget that project managers use to measure and monitor cost performance.

ANS:	cost baseline

PTS:	1	DIF:	Difficulty: Easy		REF:	p.289

OBJ:	LO: 7-5	NAT:	BUSPROG: Technology	TOP:	Determining the Budget

KEY:	Bloom's: Knowledge

16.	In addition to providing input for budgetary estimates, the process of _____ provides a cost baseline.

ANS:	cost budgeting

PTS:	1	DIF:	Difficulty: Easy		REF:	p.290

OBJ:	LO: 7-5	NAT:	BUSPROG: Technology	TOP:	Determining the Budget

KEY:	Bloom's: Knowledge

17.	A cost management plan is a subsidiary of the _____ plan.

ANS:	project management

PTS:	1	DIF:	Difficulty: Easy		REF:	p.290

OBJ:	LO: 7-5	NAT:	BUSPROG: Technology	TOP:	Determining the Budget

KEY:	Bloom's: Knowledge

18.	_____ is a project performance measurement technique that integrates scope, time, and cost data.

ANS:	Earned value management (EVM)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.291

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

19.	A(n)_____ is the original project plan plus approved changes.

ANS:	baseline

PTS:	1	DIF:	Difficulty: Easy		REF:	p.291

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

20.	The ratio of actual work completed to the percentage of work planned to have been completed at any given time during the life of the project or activity is known as the _____.

ANS:	rate of performance (RP)

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension

21.	The _____ is the portion of the approved total cost estimate planned to be spent on an activity during a given period.

ANS:	planned value (PV)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

22.	The total direct and indirect costs incurred in accomplishing work on an activity during a given period is known as the _____.

ANS:	actual cost (AC)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Analytic		TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

23.	The _____ is based on the original planned costs for the project or activity and the rate at which the team is completing work on the project or activity to date.

ANS:	earned value

PTS:	1	DIF:	Difficulty: Easy		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

24.	The _____ index is the ratio of earned value to planned value.

ANS:	schedule performance

PTS:	1	DIF:	Difficulty: Easy		REF:	p.294

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

25.	The cost performance index can be used to calculate the _____ which gives an approximate cost of completing a project based on performance to date.

ANS:	estimate at completion (EAC)

PTS:	1	DIF:	Difficulty: Easy		REF:	p.294

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Knowledge

ESSAY

1.	List and briefly describe the four project cost management processes.

ANS:

The four processes for project cost management are as follows:

(1) Planning cost management involves determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost. The main output of this process is a cost management plan.

(2) Estimating costs involves developing an approximation or estimate of the costs of the resources needed to complete a project. The main outputs of the cost estimating process are activity cost estimates, basis of estimates, and project document updates.

(3) Determining the budget involves allocating the overall cost estimate to individual work items to establish a baseline for measuring performance. The main outputs of the cost budgeting process are a cost baseline, project funding requirements, and project document updates.

(4) Controlling costs involves controlling changes to the project budget. The main outputs of the cost control process are work performance information, cost forecasts, change requests, project management plan updates, project documents updates, and organizational process assets updates.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.274-275

OBJ:	LO: 7-1	NAT:	BUSPROG: Technology

TOP:	The Importance of Project Cost Management	KEY:	Bloom's: Comprehension

2.	What are tangible and intangible costs? Distinguish between direct and indirect costs and give examples of each.

ANS:

Tangible and intangible costs and benefits are categories for determining how well an

organization can define the estimated costs and benefits for a project. Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars.

Conversely, intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms. Intangible benefits for projects often include items like goodwill, prestige, and general statements of improved productivity that an organization cannot easily translate into dollar amounts. Because intangible costs and benefits are difficult to quantify, they are often harder to justify.

Direct costs are costs that can be directly related to producing the products and services of the project. One can attribute direct costs directly to a certain project. Project managers should focus on direct costs, since they can control them. For example, direct costs include the salaries of people working full time on the project and the cost of hardware and software purchased specifically for the project. Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project. For example, the cost of electricity, paper towels, and so on in a large building housing a thousand employees who work on many projects would be indirect costs. Indirect costs are allocated to projects, and project managers have very little control over them.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.278

OBJ:	LO: 7-2	NAT:	BUSPROG: Analytic

TOP:	Basic Principles of Cost Management		KEY:	Bloom's: Comprehension

3.	What are the three basic types of cost estimating? Describe each type.

ANS:

The three basic types of cost estimating are as follows:

(1) A rough order of magnitude (ROM) estimate provides an estimate of what a project will cost. This type of estimate is done very early in a project or even before a project is officially started. Project managers and top management use this estimate to help make project selection decisions. The timeframe for this type of estimate is often three or more years prior to project completion. A ROM estimate’s accuracy is typically –50 percent to +100 percent, which means that the project’s actual costs could be 50 percent below the ROM estimate or 100 percent above. For information technology project estimates, this accuracy range is often much wider. ROM estimates are also known as a ballpark estimate, a guesstimate, a swag, or a broad gauge.

(2) A budgetary estimate is used to allocate money into an organization’s budget. Many organizations develop budgets at least two years into the future. Budgetary estimates are made one to two years prior to project completion. The accuracy of budgetary estimates is typically –10 percent to +25 percent, meaning the actual costs could be 10 percent less or 25 percent more than the budgetary estimate.

(3) A definitive estimate provides an accurate estimate of project costs. Definitive estimates are used for making many purchasing decisions for which accurate estimates are required and for estimating final project costs. Definitive estimates are made one year or less prior to project completion. A definitive estimate should be the most accurate of the three types of estimates. The accuracy of this type of estimate is normally –5 percent to +10 percent, meaning the actual costs could be 5 percent less or 10 percent more than the definitive estimate.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.280-281

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

4.	Describe three tools used in developing a good cost estimate.

ANS:

Several tools and techniques can be used to create a cost estimate. Three of such tools are as follows:

(1) Analogous estimates: They use the actual cost of a previous, similar project as the basis for estimating the cost of the current project. This technique requires a good deal of expert judgment and is generally less costly than other techniques, but it is also less accurate. Analogous estimates are most reliable when the previous projects are similar in fact, not just in appearance. In addition, the groups preparing cost estimates must have the needed expertise to determine whether certain parts of the project will be more or less expensive than analogous projects.

(2) Bottom-up estimates: They involve estimating the costs of individual work items or activities and summing them to get a project total. This approach is sometimes referred to as activity-based costing. The size of the individual work items and the experience of the estimators drive the accuracy of the estimates. Using smaller work items increases the accuracy of the cost estimate because the people assigned to do the work develop the cost estimate instead of someone unfamiliar with the work. The drawback with bottom-up estimates is that they are usually time-intensive and therefore expensive to develop.

(3) Parametric estimating: They use project characteristics (parameters) in a mathematical model to estimate project costs. Parametric models are most reliable when the historical information used to create the model is accurate, the parameters are readily quantifiable, and the model is flexible in terms of the project’s size.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.283

OBJ:	LO: 7-4	NAT:	BUSPROG: Technology	TOP:	Estimating Costs

KEY:	Bloom's: Comprehension

5.	Earned value management involves calculating three values for each activity or summary

activity from a project’s WBS. Describe each of these three values with examples.

ANS:

(1) The planned value (PV), also called the budget, is that portion of the approved total cost estimate planned to be spent on an activity during a given period. Suppose a project included a summary activity of purchasing and installing a new Web server. Suppose further that, according to the plan, it would take one week and cost a total of $10,000 for the labor hours, hardware, and software involved. The planned value (PV) for that activity that week is, therefore, $10,000.

(2) The actual cost (AC) is the total direct and indirect costs incurred in accomplishing work on an activity during a given period. For example, assume that it actually took two weeks and cost $20,000 to purchase and install the new Web server. Assume that $15,000 of these actual costs were incurred during Week 1 and $5,000 was incurred during Week 2. These amounts are the actual cost (AC) for the activity each week.

(3) The earned value (EV) is an estimate of the value of the physical work actually completed. It is based on the original planned costs for the project or activity and the rate at which the team is completing work on the project or activity to date. The rate of performance (RP) is the ratio of actual work completed to the percentage of work planned to have been completed at any given time during the life of the project or activity. For example, suppose that the server installation was halfway completed by the end of week 1. The rate of performance would be 50 percent (50/100) because by the end of week 1, the planned schedule reflects that the task should be 100 percent complete and only 50 percent of that work has been completed.

PTS:	1	DIF:	Difficulty: Moderate		REF:	p.292

OBJ:	LO: 7-6	NAT:	BUSPROG: Technology	TOP:	Controlling Costs

KEY:	Bloom's: Comprehension