# EPOS 2000 Project

# PREFACE

This is a case study of a project to develop and roll out a store system for Supersave Stores. A store system is the totality of software and hardware needed to operate a store. The name Supersave is fictitious, but the events described are based on a real project.

# SUPERSAVE PERSPECTIVE:

Supersave Stores is a recently created food retailing company formed by the amalgamation of three already-established supermarket chains - Alpha, Beta, and Gamma. These chains are now owned and managed by Supersave. The owners of Supersave are a consortium of German and Swiss business executives with wide interests in food manufacturing and distribution. The consortium has a strategic plan prepared with the help of a leading firm of management consultants. The plan seeks to establish an upmarket, profitable supermarket chain and then to embark on an expansion program into countries of the former Eastern Bloc and Russia. Supersave has called its plan EPOS 2000.

# EPOS 2000

[Student Note: The need for a wide-area network (WAN) connection to a financial institution is recognized but is intentionally omitted to limit the assignment duration.]

Electronic communication is absolutely key to the plan. Supersave needs real-time stock and item movement data to link its store operations with its food distribution and manufacturing centers throughout Europe and the former USSR to enable stock replenishment and price management. The first phase of the plan is to refurbish the 229 acquired stores (from Alpha, Beta, and Gamma), and install state-of-the-art computer systems.

Two days ago (23 February), Supersave issued an RFP to three equipment suppliers - IBM, Siemans Nixdorf, and Fujitsu ICL - for the development of a store system and the supply and roll out of the store equipment to its 229 existing and 21 planned stores. (See the statement of requirements.)

A store system is one that provides electronic point of sale (EPOS) and back-office applications. These two major units are commonly called front end and back office. The front end is the customer-facing application - the servicing of a customer checking out and the administrative procedures associated with maintaining the checkout registers. The back office is where all of the administrative procedures required for running the store are performed.

## Alpha Chain

Alpha (Poland) has 27 stores and is a non-IBM account. It has a variety of computer equipment, most of which are Russian. Its front end is not EPOS. Supersave acquired this small chain to evaluate and solve any problems it might have operating supermarkets in the former Eastern Bloc and the former USSR. The largest store has 15 checkout lanes. Supersave intends to open 3 new stores with up to 30 lanes.

## Beta Chain

Beta (U.K.) has 92 stores (the largest has 30 checkout lanes) and is also a non-IBM account (Fujitsu ICL). It has an EPOS front end ready for replacement (all registers are 6 to 10 years old). Beta is an experienced information technology (I/T) user. Supersave plans to build 8 new stores, each with 50 checkout lanes.

Supersave has very interesting plans for this chain as it plans to diversify into a variety of financial applications and customer loyalty programs. Supersave intends to provide banking services, offering facilities for deposit, withdrawal, savings, direct transfer, loans, and credit cards. All of these services are to be provided at the supermarket’s checkout lanes. Supersave believes it will be able to beat the established banks on savings and loan rates and convenience of service because it will not carry the overhead that traditional banks incur for real estate and dedicated staff. All Supersave needs is the computer systems!

## Gamma Chain

Gamma (Germany) has been an IBM customer for more than 5 years. It has a forward-thinking management team, but was overextended in its capital investment program - hence its vulnerability to takeover. It was planning to build its store systems in two phases - first the back office, then the front end. It has been working for 2 years on a set of custom-built back-office applications (known as the Store Application Programs (SAP)) running on an RS/6000 under AIX and connected over an X.25 WAN to a central server. When these were operational, it intended to go to the second phase, which was to replace the EPOS front end. Its current registers are Nixdorf, varying in age from 4 to 7 years. An IBM team from the Retail Industry Solution Unit (Retail ISU) Account Team spent 3 months helping Gamma to specify the functions required of the new EPOS checkout system. A letter of intent for 40 RS/6000s and ancillary equipment was on the point of being sent to IBM when the takeover took place. At that point, all plans were shelved pending award of contract for the EPOS 2000 equipment.

Gamma has 110 stores, the largest of which has 30 checkout lanes. Supersave intends to build 10 new stores, each with 50 checkout lanes.

# EPOS 2000 PROJECT

EPOS 2000 has been split into five subprojects:

- Development of the systems to be installed in each store, known as the Store System Project (target delivery date November, this year)

- Development of the systems to be installed in the server sites in Germany, U.K., and Poland (target delivery date November, this year)

- Refurbishment of the existing 229 stores

- Building of 21 new stores (opening 2 years from now)

- Roll out of the store system to the 250 stores, starting before Christmas (to be completed in 36 months)

The Store System Project and the Store Rollout Project are to be contracted to the equipment supplier. Central site development, store refurbishment, and building construction are to remain the responsibility of Supersave.

# CUSTOMER STATEMENT OF REQUIREMENT

Supersave requires the supplier to provide a storewide checkout system and to install it in 250 stores. The supplier also is requested to provide, in each of the 250 stores, a store processing capability for Supersave Store Applications. These applications must communicate with server processors on an intranet network and have access to sales transaction data to be provided by the checkout system.

## Project Level Requirements

Supersave has the following mandatory requirements:

- Communication protocols across wide-area networks must conform to open systems foundation (OSF) guidelines.

- The store processor must run on a UNIX, or UNIX-equivalent platform.

- The software in all stores, regardless of size, must be the same.

- The supplier must take responsibility for the integration of the store system and deliver a system that is operationally ready within 6 months of award of contract.

- The store installation program must be completed within 42 months of contract award.

## Checkout System

Supersave requires the following equipment on each checkout lane:

- A laser bar-code scanner

- A register for operation in the seated position equipped with digital display, tally-roll printer, cash drawer, keyboard, product identification number (PIN) reader display, and check printer

- A register that is programmable and capable of performing the sales transactions as currently performed, plus the following:

  - Three hard totals for accumulated cash in different currencies

  - Hard total log on operator change

  - Direct debit tender

  - Tender on account

  - Credit-card tender

  - Loyalty-card credit

  - Tender in different/mixed currencies (up to three)

  - Check printer format change (up to three format options)

- A register that supports facilities for the following on-line banking transactions:

  - Deposit

  - Withdrawal

  - Account status check

  - Loans

  - Loan authorization check

  - Loan repayment

  - Loan status check

- The system must be capable of handling an average throughput rate of 1,000 items per lane per hour. (For a 50-lane store, the system must handle a volume of 50,000 items per hour.)

- The system must be capable of a data currency of not less than 5 minutes (data must be available for processing by the back-office application programs not less than 5 minutes from an end of transaction).

- The system must be capable of sustaining continuous trading 7 days a week, 24 hours a day. In the event of component failure or removal of any component for servicing, the fallback and recovery provisions should allow trading to continue without interruption and without data loss. Restart after component failure must be automatic - the system must be capable of detecting a recovered component and repositioning the system without operator intervention.

- Item movement data must be consolidated across the store. Transaction data must be consolidated across the store.

- The above data must be accessible by the Supersave Store Application programs without the need for source code changes. The system must allow item price changes during trading hours synchronized across all registers. The system must provide facilities for receipt and transmission of files between the store and a remote processor.

## Roll Out

The supplier must roll out the store system to 250 stores situated in three operating countries -Germany, Poland, and the United Kingdom (120 stores in Germany, 100 stores in the U.K., and 30 stores in Poland). Installation must commence in each country within 6 months of award of contract and must be complete within 42 months of award of contract. A preliminary store installation schedule is available on request.

Supersave requires that the supplier perform the following activities in all stores:

- Cabling of registers

- Installation of equipment

- Loading of software (including the Supersave applications)

- Enabling of all systems

- Demonstration that all systems are performing as specified

The supplier also must provide assistance on the store site for a period of 1 month after installation.

## Penalties

The supplier shall pay Supersave Stores in the event that any store fails to trade because of late installation (as defined in the store installation schedule) of the store system, a sum of €10,000 for each trading day lost.